## AMMM OTD 306090
MCS ACO Code | ECS LOB | Contract Number | Delivery Order | GK Platform | MCS ISP Code | MCS PIIN | MCS SPIIN | MCS Line Item ID | MCS Noun | MCS Delivery Schedule Date | WB ECD | GK CLIN Program Manager | High-Level Delivery Status | WB Status | WB Comments | MCS Bal Qty Shed | WB CLIN Status POC | GK LM Contracts POC | ECS CLIN Description | MCS Part Number | MCS Current Status | MCS Contract Purpose | MCS Contract Type | MOCAS Delivery Due Date | MCS Service Completion Date | concat
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AB | ADDITIONAL | 2020-06-19 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697927-1 / Qty 1 / Sales Order 10069090 / DO 82972116 (CVA0009) Accepted in WAWF 5/6/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-06-19 |  | FA8504-18-F-00502006AB44001
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AE | ADDITIONAL | 2020-08-20 | 2019-12-20 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; DO 82825172 (CVA0002) in WAWF awaiting DCMA acceptance | 0 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 697941-3 | 1 | 1 | J | 2020-08-20 |  | FA8504-18-F-00502006AE44063
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AF | ADDITIONAL | 2020-07-20 | 2020-06-15 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO# 83064295/ processing in shipping | -1 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 3291272-2-3 | 1 | 1 | J | 2020-07-20 |  | FA8504-18-F-00502006AF44032
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AH | ADDITIONAL | 2020-06-19 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697922-5 / Qty 1 / Sales Order 10069095 / DO 82925887 (CVA0007) Accepted in WAWF 3/27/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 697922-5 | 1 | 1 | J | 2020-06-19 |  | FA8504-18-F-00502006AH44001
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AA | ADDITIONAL | 2020-05-01 | 2020-03-30 | Avery D Jones | ON TIME | DD250 Accepted In WAWF | PN 697923-3 / Qty 1 / Sales Order 10069089 / DO 82940115 (CVA0017) Accepted in WAWF 3/27/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) APU CONTROL PANEL, PN 697923-3, NSN: 6110-01-438-1846 | 697923-3 | 1 | 1 | J | 2020-05-01 |  | FA8504-18-F-00682006AA43952
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AC | ADDITIONAL | 2020-08-31 | 2020-06-30 | Eric Hall | ON TIME |  | On track; P-Coded part. ECD 6/30/2020. PN 63880-104 / SO 10069047..Mod POP extended to 8/31/2020 | -2 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) LIFE RAFT, 46-MAN, PN 63880-104; NSN: 4220-01-483-3204 | 63880-104 | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-00682006AC44074
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AE | ADDITIONAL | 2020-06-01 | 2020-05-13 | Avery D Jones | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working on creating a delivery order in L12 | -3 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) AUX VENT VALVE, PN 3291272-2-3; NSN: 4810-01-583-9245 | 3291272-2-3 | 1 | 1 | J | 2020-06-01 |  | FA8504-18-F-00682006AE43983
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AF | ADDITIONAL | 2020-07-01 | 2020-07-01 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | DO# 82974423/ DO# 83030215- processing in shipping. 2ea still to delivery by June to support. Working with buyer. | -4 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) GENERATOR, ENGINE, PN 697970-3; NSN: 2925-01-541-5012 | 697970-3 | 1 | 1 | J | 2020-07-01 |  | FA8504-18-F-00682006AF44013
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AG | ADDITIONAL | 2020-06-01 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697903-3 / Qty 4 / Sales Order 10069087 / DO 82898189 (CVA0011) Accepted in WAWF 03/12/2020, DO 82908828 (CVA0012) Accepted in WAWF on 4/17/2020 / DO 82914633 (CVA0013) Accepted in WAWF on 2/28/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) PANEL ASSEMBLY, PN 697903-3; NSN: 6110-01-447-3148 | 697903-3 | 1 | 1 | J | 2020-06-01 |  | FA8504-18-F-00682006AG43983
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AJ | ADDITIONAL | 2020-05-01 | 2020-05-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697922-5 / Qty 9 / Sales Order 10069086 / DO 82925888 (CVA0014 ) Accepted in WAWF 3/27/2020, DO 82928652 (CVA0015) Accepted in WAWF 3/12/2020, DO 82934381 (CVA0016) Accepted in WAWF 3/27/2020, DO 82940114 (CVA0018) Accepted in WAWF 4/03/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) CONTROL PANEL, PN 697922-5; NSN: 6110-01-472-3531 | 697922-5 | 1 | 1 | J | 2020-05-01 |  | FA8504-18-F-00682006AJ43952
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AL | ADDITIONAL | 2020-08-31 | 2020-06-05 | Eric Hall | AT RISK | Other | Not on track; P-Coded part. PO 6534855408 due 6/5/2020. PN 63880-103 / SO 10069051..in process of requesting late delivery authorization. | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) LIFE RAFT, 46 MAN, PN 63880-103; NSN: 4220-01-483-3201 | 63880-103 | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-00682006AL44074
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AP | ADDITIONAL | 2020-05-01 | 2020-05-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697918-1 / Qty 1 / Sales Order 10069085 / DO 82947444 (CVA0019) Accepted in WAWF 4/1/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) PANEL, LANDING GEAR & LIGHTS, PN 697918-1; NSN: 6110-01-433-5000 | 697918-1 | 1 | 1 | J | 2020-05-01 |  | FA8504-18-F-00682006AP43952
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0080 | C130 | AOR | FA8504-18-F-0080 |  | 2006 | ADDITIONAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) FLAP ASSEMBLY, OUTER WING, PN 3352602-1 |  | 1 | 1 | J | 2020-06-30 | 2020-06-30 | FA8504-18-F-00802006
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0083 | C130 | AOR | FA8504-18-F-0083 |  | 2006AC | EQUIPMENT | 2020-08-31 |  | Eric Hall | AT RISK |  |  | 0 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-00832006AC44074
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0083 | C130 | AOR | FA8504-18-F-0083 |  | 2006AD | EQUIPMENT | 2020-08-31 |  | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; P-Coded part. ECD 6/30/2020. PN 63880-104 / SO 10069054..Mod POP extended to 8/31/2020 | -2 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-00832006AD44074
ALK | Other | FA8504-16-D-0001 | FA8504-18-F-0084 | C130 | AOR | FA8504-18-F-0084 |  | 2006AA | EQUIPMENT | 2020-06-30 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697927-1 / Qty 1 / Sales Order 10069083 / DO 82966300 (CVA0006) Accepted in WAWF on 4/28/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-06-30 |  | FA8504-18-F-00842006AA44012
ALV | Other | FA8504-20-C-0002 |  | C130 | AOI | FA8504-20-C-0002 |  | 0006 | PROGRAM MAN | 2020-06-17 |  | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track | -1 |  | Olivia M Haller |  |  | 1 | 1 | J | 2020-06-17 |  | FA8504-20-C-0002000643999
ALX | Other | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 1500 | ALL WORK | 2020-06-24 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | AC 6 MOD Ahead of schedule | -1 |  | Alicia N Walker | OPTION FIVE - MODIFICATION INSTALLATION AIRCRAFT 6 |  | 1 | 2 | U | 2020-06-24 |  | FA8509-19-F-0001150044006
ALX | Other | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 4500 | SERVICE | 2020-06-24 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | O&A Work associated with MOD of AC 6 | -1 |  | Alicia N Walker | OVER AND ABOVE WORK (O&AW) (SUPPORTING AIRCRAFT #6 MODIFICATION INSTALLATION) |  | 1 | 2 | U | 2020-06-24 |  | FA8509-19-F-0001450044006
ALA | Other | FA8553-19-D-0001 | FA8553-20-F-0002 | C130 | AOI | FA8553-20-F-0002 |  | 0010 | KNOBS | 2020-08-12 |  | Kathleen M Atkins | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Tracking to delivery date | -10 |  | Alicia N Walker | C-130J SPARES KNOBS | GP606-V105 | 1 | 1 | J | 2020-08-12 |  | FA8553-20-F-0002001044055
ALA | Other | FA8553-19-D-0001 | FA8553-20-F-0012 |  | AOI | FA8553-20-F-0012 |  | 1010AB | [10 empty] | GASKETS | GASKET | 1 | 1 | J | 2020-08-10 | 2020-08-10 | FA8553-20-F-00121010AB
ALV | Other | FA8625-14-C-6450 |  | C130 | AOH | FA8625-14-C-6450 |  | 6003 | AF16HC130J | 2020-06-30 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5895 | 0 |  | Mary Kathleen Chaney | FY16 USAF HC-130J |  | 1 | 1 | L | 2020-06-30 |  | FA8625-14-C-6450600344012
ALV | Other | FA8625-14-C-6450 |  | C130 | AOH | FA8625-14-C-6450 |  | 6006 | MC17KC130J | 2020-07-31 |  | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5896 | 0 |  | Mary Kathleen Chaney | FY17 KC-130J AIRCRAFT |  | 1 | 1 | L | 2020-07-31 |  | FA8625-14-C-6450600644043
ALK | Other | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0008 | HC-130J INC | 2020-07-31 | 2020-07-30 | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CSO 2.5 Kit | -1 |  | Belinda C Young | HC-130J INC 2.5 CSO STATION KIT & TCTO |  | 1 | 2 | V | 2020-07-31 |  | FA8625-15-D-65910002000844043
ALK | Other | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0009 | HC-130J INC | 2020-07-31 | 2020-07-30 | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CSO 2.5 Installs | -1 |  | Belinda C Young | HHC-130J INC 2.5 CSO STATION TKI AT GSO |  | 1 | 2 | V | 2020-07-31 |  | FA8625-15-D-65910002000944043
ALK | Other | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0010 | HC-130J INC | 2020-08-19 |  | Jeff T Vach | AT RISK |  |  | -1 |  | Belinda C Young | HC-130J INC 2.5 CSO STATION KIT FOR SACU |  | 1 | 2 | V | 2020-08-19 |  | FA8625-15-D-65910002001044062
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1401 | ANALYSIS | 2020-08-18 |  | Jim Armor | AT RISK |  |  | -5 |  | Mariah Callins | OPTION YEAR 3 ENGINEERING AND LOGISTICS SUPPORT |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000140144061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1403 | MANUAL | 2020-08-15 |  | Jackie L Macedonia | AT RISK |  |  | -6 |  | Mariah Callins | OPTION YEAR 3 HC/MC/AC TECHNICAL MANUAL CONTRACT REQUIREMENTS |  | 1 | 1 | U | 2020-08-15 |  | FA8625-16-F-7000140344058
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1407 | PROGRAM | 2020-08-18 |  | Jim Armor | AT RISK |  |  | -5 |  | Mariah Callins | OPTION YEAR 3 RELIABILITY MAINTAINABILITY PROGRAM |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000140744061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1410 | OPTION YEAR | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -5 |  | Mariah Callins | OPTION YEAR 3 FIELD SERVICE REPRESENTATIVE - EGLIN |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000141044061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 3401 | OPTION YEAR |  |  | Jim Armor | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 3 TRAVEL |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70003401
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4404 | CPFF |  |  | Chris Price | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 3 - DIMINISHING MANUFACTURING SOURCES STUDIES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70004404
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4405 | OPTION YEAR |  |  | Jim Armor | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 3 - ENGINEERING SUPPORT SERVICES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70004405
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4407 | CPFF |  |  | Chris Price | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 2 BU 7/8.1 RETROFIT DMS STUDIES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70004407
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4501 | DEFICIENCY |  |  | Jim Armor | AT RISK |  |  |  |  | Mariah Callins | DEFICIENCY REPORTING (DR) OPTION YEAR 2 (CPFF) |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70004501
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4502 | DR TRAVEL ( |  |  | Jim Armor | AT RISK |  |  |  |  | Mariah Callins | DR TRAVEL (OPTION) |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-70004502
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1034 | HC/MC-130J | 2020-05-29 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | HC/MC-130J YEAR 2 TECHNICAL MANUAL & DATA (NON IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103443980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1035 | HC/MC-130J | 2020-05-29 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | HC/MC YEAR 2 TECHNICAL MANUAL & DATA (IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103543980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1036 | HC/MC-130J | 2020-05-29 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | HC/MC-130J YEAR 2 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103643980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1037 | AC-130J YEA | 2020-05-29 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | AC-130J YEAR 2 TECHNICAL MANUAL DATA (NON-IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103743980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1038 | AC-130J YEA | 2020-05-29 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | AC-130J YEAR 2 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103843980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1039 | AC-130J YEA | 2020-05-29 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | AC-130J YEAR 2 TECHNICAL MANUAL & DATA (FLIGHTPPP) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150103943980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1040 | SACU TECHNI | 2020-05-29 | 2020-05-29 | Jackie L Macedonia | AT RISK | Contract Modification Expected to Change PoP Date | PCOL 20-0064 received 21 April requesting incorporation of SACU data in November 2020 Pubs Update. LM requested POP extension through December 2020 to accommodate USG request. | -1 | Sonya J Young | Brittany N Scott | SACU TECHNICAL MANUAL & DATA (NON IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150104043980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1041 | SACU TECHNI | 2020-05-29 | 2020-05-29 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | SACU TECHNICAL MANUAL & DATA (IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150104143980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1042 | SACU TECHNI | 2020-05-29 | 2020-05-29 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -1 | Sonya J Young | Brittany N Scott | SACU TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150104243980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1051 | VH1 TECH OR | 2020-05-29 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | -49 | Sonya J Young | Brittany N Scott | AC-130J VH1 TECH ORDER CHANGE PAGES (NON IPB) |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150105143980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1054 | AC-130J SID | 2020-05-29 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | 0 | Sonya J Young | Brittany N Scott | AC-130J SIDE HUD TCTO |  | 1 | 1 | J | 2020-05-29 |  | FA8625-16-F-7150105443980
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1055 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -1657 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (NON-IPB) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150105544061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1056 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -28 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB < 50 PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150105644061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1057 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -49 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB 50+ PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150105744061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1058 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -1934 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150105844061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1059 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -3035 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (NON-IPB) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150105944061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1060 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -28 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB < 50 PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150106044061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1061 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -1550 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB 50+ PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150106144061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1062 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | -4030 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150106244061
ALX | Other | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1071 | PROPOSAL PR | 2020-08-18 |  | Jackie L Macedonia | AT RISK |  |  | 0 |  | Brittany N Scott | PROPOSAL PREPARATION |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150107144061
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0011 | PROGRAM DEP |  |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Contract Mod required to de-scope teach Mod |  | Matt Tyler | Nalysha S Jones | PROGRAM DEPOT MAINTENANCE TYPE 1 TRAINING & MATERIAL |  | 1 | 1 | U | 2020-05-29 | 2020-05-29 | FA8625-17-C-65890011
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0015 | CNS/ATM TRA | 2020-07-30 |  | Matt Tyler | AT RISK |  |  | -1 | Matt Tyler | Nalysha S Jones | CNS/ATM TRAVEL |  | 1 | 1 | U | 2020-07-30 |  | FA8625-17-C-6589001544042
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0016 | TECHNICAL D | 2020-06-30 |  | Matt Tyler | AT RISK |  |  | -1 | Matt Tyler | Nalysha S Jones | TECHNICAL DATA PACKAGE (TDP) FOR WEAPON SYSTEM TRAINERS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589001644012
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0018 | FINAL TECHN | 2020-06-30 |  | Matt Tyler | AT RISK |  |  | -1 | Matt Tyler | Nalysha S Jones | FINAL TECHNICAL DATA PACKAGE (TDP) FOR WEAPON SYSTEM TRAINERS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589001844012
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0019 | WEAPON SYST | 2020-06-30 |  | Matt Tyler | AT RISK |  |  | -1 | Matt Tyler | Nalysha S Jones | WEAPON SYSTEM TRAINER MODIFICATION |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589001944012
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0027 | INITAL CADR | 2020-07-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | COC Submitted to USAF, Awtg PCO Concurrence to Close | 0 | Matt Tyler | Nalysha S Jones | INITIAL CADRE QUAL MAINTENANCE TRAINING AND MATERIAL |  | 1 | 1 | U | 2020-07-30 |  | FA8625-17-C-6589002744042
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 1423DD | DATA |  |  | Matt Tyler | ON TIME |  | Placeholder - not deliverable CLIN |  | Matt Tyler | Nalysha S Jones |  |  | 1 | 1 | U | 2020-05-29 | 2020-05-29 | FA8625-17-C-65891423DD
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | B001 | DATA | 2020-05-29 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | 0 | Matt Tyler | Nalysha S Jones |  |  | 1 | 1 | U | 2020-05-29 |  | FA8625-17-C-6589B00143980
ALQ | Other | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | C009 | DATA | 2020-05-29 |  | Matt Tyler | AT RISK | Contract Modification Expected to Change PoP Date |  | 0 | Matt Tyler | Nalysha S Jones |  |  | 1 | 1 | U | 2020-05-29 |  | FA8625-17-C-6589C00943980
ALX | Other | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2001 | FY18 HC-130 | 2020-07-31 |  | James B Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5897 | -2 |  | Mariah Callins | FY17 C-130J-30 AIRCRAFT |  | 1 | 1 | J | 2020-07-31 |  | FA8625-17-F-7010200144043
ALX | Other | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2002 | AIRCRAFT | 2020-08-31 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5898 | -1 |  | Mariah Callins |  |  | 1 | 1 | J | 2020-08-31 |  | FA8625-17-F-7010200244074
ALX | Other | FA8625-16-D-6458 | FA8625-17-F-7152 | C130 | AOA | FA8625-17-F-7152 |  | 8006 | SYSTEM | 2020-08-04 |  | Jeff T Vach |  |  |  | -1 |  | Alicia N Walker | OPTION I - DATA TRANSER & DIAGNOSTIC SYSTEMS (DTADS) SUPPORT |  | 1 | 1 | J | 2020-08-04 |  | FA8625-17-F-7152800644047
ALX | Other | FA8625-16-D-6458 | FA8625-17-F-7163 | C130 | AOA | FA8625-17-F-7163 |  | 0001 | CIP-01 SOFT | 2020-08-31 |  | Jeff T Vach |  |  |  | -1 |  | Belinda C Young | CIP-01 SOFTWARE MERGER |  | 1 | 1 | J | 2020-08-31 |  | FA8625-17-F-7163000144074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1623 | UMSC KC-130 |  | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Lot 1 RoR USMC Services as required, CoC to close out |  |  | Mary Kathleen Chaney | ICS ROR - LOT 1 - OPTION YEAR 1 - USMC KC-130J |  | 1 | 1 | L | 2020-07-31 | 2020-07-31 | FA8625-18-F-70011623
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1801 | CNI-SP LIFE | 2020-08-30 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - C130J (STRETCH/SHORT) |  | 1 | 1 | L | 2020-08-30 |  | FA8625-18-F-7001180144073
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1803 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - USMC - KC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001180344074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1804 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - USCG HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001180444074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1806 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI SP - LIFETIME BUY - AFSOC MC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001180644074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1807 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - ACC HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001180744074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1808 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - SYSTEMS INTEGRATION MGMT |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001180844074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1811 | UCA - CNI-S | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | UCA- CNI-SP RISC MICROPROCESSOR LAST TIME BUY - AMC C-130J (STRETCH/SHORT) |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001181144074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1813 | UCA - CNI-S | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | UCA- CNI-SP RISC MICROPROCESSOR LAST TIME BUY - USMC KC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001181344074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1814 | UCA - CNI-S | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | UCA- CNI-SP RISC MICROPROCESSOR LAST TIME BUY - USCG HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001181444074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1817 | UCA - CNI-S | 2020-08-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | UCA- CNI-SP RISC MICROPROCESSOR LAST TIME BUY - ACC HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001181744074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2101 | UPGRADE | 2020-06-30 | 2020-06-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | COC for CEVA Support Service | -1 |  | Mary Kathleen Chaney | KITS - LOT 1 - CEVA SUPPORT |  | 1 | 1 | L | 2020-06-30 |  | FA8625-18-F-7001210144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2111 | BLOCK UPGRA | 2020-07-16 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track | -2 |  | Mary Kathleen Chaney | KITS - C130J - (STRETCH) - GROUP A - QTY 16 |  | 1 | 1 | L | 2020-07-16 |  | FA8625-18-F-7001211144028
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2112 | BLOCK UPGRA | 2020-07-16 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track | -2 | Daniel L Kiefer | Mary Kathleen Chaney | KITS - C130J - (STRETCH) - GROUP B - QTY 16 |  | 1 | 1 | L | 2020-07-16 |  | FA8625-18-F-7001211244028
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2131 | SUPPLIES/SE | 2020-05-13 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | -1 |  | Mary Kathleen Chaney | KITS - KC130J - GROUP A & B |  | 1 | 1 | L | 2020-05-13 |  | FA8625-18-F-7001213143964
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2141 | BLOCK UPGRA | 2020-05-15 |  | James H Porter | AT RISK | Contract Mod Requested | Material Survey for P/N 885368-27704 - No ECD from QA | -1 | Daniel L Kiefer | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-05-15 |  | FA8625-18-F-7001214143966
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2141 | BLOCK UPGRA | 2020-05-16 |  | James H Porter | AT RISK | Contract Mod Requested | Material Survey for P/N 885368-27704 - No ECD from QA | -1 | Daniel L Kiefer | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-05-16 |  | FA8625-18-F-7001214143967
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2141 | BLOCK UPGRA | 2020-06-03 | 2020-06-03 | James H Porter | AT RISK | Contract Mod Requested | Material Survey for P/N 885368-27704 - No ECD from QA | -1 | Daniel L Kiefer | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-06-03 |  | FA8625-18-F-7001214143985
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2193 | SUPPLIES/SE | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | MOD LINE SPARES - KC130J |  | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001219344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2199 | UPGRADE | 2020-07-31 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | MOD LINE SPARES - CEVA SUPPORT |  | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001219944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2293 | BLOCK UPGRA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | MOD LINE SPARES - LOT 2 - KC130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001229344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2297 | BLOCK UPGRA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | MOD LINE SPARES - ACC-HC-130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001229744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2299 | BLOCK UPGRA | 2020-07-24 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | MOD LINE SPARES - LOT 2 - CEVA |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001229944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2421 | INITIAL SPA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | INITIAL SPARES - LOT 2 - C103J - STRETCH/ SHORT/ACC HC130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001242144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2423 | INITIAL SPA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | INITIAL SPARES - LOT 2 - KC130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001242344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2429 | LOT 2 - CEV | 2020-07-24 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | INITIAL SPARES - LOT 2 - CEVA |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001242944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2512 | UCA - TRAIN | 2020-07-02 | 2020-07-02 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - TRAINER DEVICE HARDWARE FROM LOT 1 - AMC C-130J (STRETCH/SHORT) |  | 1 | 1 | L | 2020-07-02 |  | FA8625-18-F-7001251244014
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2514 | UCA - TRAIN | 2020-06-01 | 2020-06-01 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - TRAINER DEVICE HARDWARE FROM LOT 1 - USMC KC-130J |  | 1 | 1 | L | 2020-06-01 |  | FA8625-18-F-7001251443983
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2519 | UCA - TRAIN | 2020-06-05 | 2020-06-05 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - TRAINER DEVICE HARDWARE FROM LOT 1 - CEVA AM |  | 1 | 1 | L | 2020-06-05 |  | FA8625-18-F-7001251943987
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2523 | TRAINER DEV | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | TRAINER DEVICE HARDWARE & INITIAL SPARES - LOT 2 - KC130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001252344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2527 | TRAINER DEV | 2020-07-24 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | TRAINER DEVICE HARDWARE & INITIAL SPARES - LOT 2 - ACC-HC-130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001252744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2529 | TRAINER DEV | 2020-07-24 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | TRAINER DEVICE HARDWARE & INITIAL SPARES - LOT 2 - CEVA |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001252944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2621 | READINESS S | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | READINESS SPARES PACKAGES - LOT 2 - C130J - STRETCH & SHORT |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001262144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2627 | READINESS S | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Top level CLIN | -1 |  | Mary Kathleen Chaney | READINESS SPARES PACKAGES - LOT 2 - ACC - HC-130J |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001262744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2629 | READINESS S | 2020-07-24 |  | James H Porter | AT RISK |  |  | -1 |  | Mary Kathleen Chaney | READINESS SPARES PACKAGES - LOT 2 - CEVA |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001262944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2812 | UPGRADE | 2020-05-31 | 2020-05-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Upgrade Services CLIN, will close if not used at end of PoP | -2 |  | Mary Kathleen Chaney | GFE HUD HEU UPGRADE - C130J - SHORT |  | 1 | 1 | L | 2020-05-31 |  | FA8625-18-F-7001281243982
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 4021 | PREPARATION | 2020-05-05 | 2020-05-05 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | COC to close out last day of PoP | -1 |  | Mary Kathleen Chaney | PROPOSAL PREPARATION |  | 1 | 1 | L | 2020-05-05 |  | FA8625-18-F-7001402143956
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 9010 | UCA - PECUL | 2020-06-12 | 2020-06-12 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - PECULIAR SUPPORT EQUIPMENT (PSE) - USAF, USMC |  | 1 | 1 | L | 2020-06-12 |  | FA8625-18-F-7001901043994
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 9019 | UCA - USAF, | 2020-06-12 | 2020-06-12 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - USAF, USMC PECULIAR SUPPORT EQUIPMENT (PSE) |  | 1 | 1 | L | 2020-06-12 |  | FA8625-18-F-7001901943994
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H001 | GPS/WAAS | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H002 | EMU | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H003 | PMD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H004 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H005 | CS AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H006 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Douglas A Davidi | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H007 | RECEPATCLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H008 | HAND MICROP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H00944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H010 | MEMORY CD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H011 | DIPLEXER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H012 | UNIT MOUNT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-00 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H013 | TETHER CABL | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H014 | COMBINER RF | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H015 | HIGH PWR RE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H016 | TRAY ASSY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H017 | TRAY ASSY | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H018 | BLANKET UN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H01944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H020 | MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H021 | DATA UNIT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H023 | SPLITTER | 2020-07-31 | 2020-07-01 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | Meeting with USG 3/20/2019 to work out new POP extension date | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H024 | MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H025 | BROADBAND | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H026 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H027 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; DO 82545345 processing through shipping | -3 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H028 | COVER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H029 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H02944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H030 | CIRCUIT BK | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DOs 82976563, 82976824, 83001307 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H031 | ADRESS AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -4 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H032 | PILOT CONTR | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H033 | CONTROL ABY | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H034 | SPLINE | 2020-07-31 |  | James H Porter | AT RISK |  | Meeting with USG 3/20/2019 to work out new POP extension date | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H035 | CNI-SP-COUN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H036 | MISSION DIS | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -4 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H037 | SNDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H038 | VIDEO SWITC | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0640 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H039 | TRAY ASSY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H03944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H040 | DIGITAL SWI | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H041 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H042 | VHF DATA RA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H043 | PLUGA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H044 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H045 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H048 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H049 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H04944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H050 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H051 | SCREW | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H052 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H053 | SPACER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H054 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJF4V71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H056 | FLOODLIGHT | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H057 | L-BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H059 | SPEAKER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H05944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H060 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001H06044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H203 | PMD | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971190 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83028099 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H205 | CS AMP | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD 4/28/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H210 | PCMCIA MEMO | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H211 | DIGITAL SWI | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H213 | PMD TETHER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H214 | COMBINER RF | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H216 | MOUNTING TR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 4/30/20 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039974 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H218 | PRG INT BLA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H219 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039971 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039969 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H221 | SATELLITE D | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039968 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H222 | COUPLER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039964 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H223 | SLITTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0786 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H224 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0788 | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0612 | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H226 | PRINTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0642 | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H227 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -3 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H228 | HPA | 2020-07-24 |  | James H Porter |  |  |  | -1 |  | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H229 | PMD DUST CO | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039958 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H230 | PLUG | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83039949 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H231 | CIRCUIT BRE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83001309 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H233 | PILOT CONTR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H234 | COPILOT CON | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H235 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039940 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H236 | CNI-SP COUN | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0622 | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H239 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H241 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0613 | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H242 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 6/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H243 | DIGIAL CREW | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H246 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H247 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0782 | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H248 | PLUG | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039942 | -2 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H249 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H24944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H250 | PLUG | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0620 | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H251 | PLUG CONNEC | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83015686 | -2 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H252 | PLUG CONNEC | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83015689 | -2 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H253 | SCREW | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0619 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H254 | TRAY ASSEMB | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD : 6/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H255 | SPACER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0618 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H256 | TRAY ASSEMB | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0617 | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H258 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H259 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H25944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H260 | GPS/WAAS AN | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H26044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H261 | SPEAKER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H26144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H262 | ANTENNA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83061804 | -2 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001H26244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J002 | EMU | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J003 | PMD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J004 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11508080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J005 | CS AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J006 | PA PRE-AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J007 | RECEPTACLE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J008 | HAND MICROP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J00944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J010 | PCMCIA MEMO | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J011 | DIPLEXER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J012 | PMD UNIT MO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J013 | PMD TETHER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J014 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J015 | HIGH PWR RE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J016 | MOUNTING TR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J017 | MOUNTING TR | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J018 | BLANKET UN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J01944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J020 | COM MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J021 | SATELLITE D | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J023 | SPLITTER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J024 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J025 | SWITFT BROA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J026 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J027 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J028 | PMD DUST CO | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J029 | PLUG C | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J02944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J030 | CIR BREAKER | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track Processing through shipping DO 82967973 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J031 | AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J032 | PILOT CON | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J033 | PILOT CON | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J034 | SPLINE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J035 | CNI-SP COUN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J036 | MIS DISPLAY | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J037 | SMDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J038 | VIDEO SWITC | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J039 | TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J03944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J040 | DIGITAL SWI | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82966081 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J041 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J042 | VHF DATA RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J043 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J044 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J045 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J048 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J049 | PLUG CONN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J04944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J050 | PLUG CONN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J051 | SCREW | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J052 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J053 | SPACER | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 11/19/2018 / CVA0019 | -2 |  | Mary Kathleen Chaney |  | NAD43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J054 | TRAY ASBY | 2020-07-31 | 2020-07-31 | James H Porter | LATE |  | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJF6V71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J056 | FLOODLIGHT | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J057 | L BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J059 | SPEAKER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J05944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J060 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718.1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001J06044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K002 | EMU | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K003 | PMD | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K004 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K005 | CS AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K006 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K007 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K008 | HAND MICROP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K00944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K010 | PCMCIA MEMO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K011 | DIPLEXER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 222643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K012 | PMD UNIT MO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K013 | PMD TETHER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K014 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K015 | HIGH PWR RE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K016 | MOUNT TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K017 | MOUNT TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K018 | BLANKET UN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K01944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K020 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K021 | SATELLITE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K023 | SPLITTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K024 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K025 | SWIFT BROA | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82568202 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K027 | HIGH GAIN A | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 51338-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K029 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K02944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K031 | PUBLIC ADRE | 2020-07-31 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K032 | PILOT CONTR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K033 | COPILOT CON | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K034 | SPLINE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K035 | CNI-SP COUN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K036 | MISSION DIS | 2020-07-31 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K037 | SMDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K038 | VIDEO SWITC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K039 | TRAY ASSY/V | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K03944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K040 | DIGITAL SWI | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K041 | DIGITAL CRE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K042 | VHF DATA RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K043 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K044 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K045 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K048 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K049 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K04944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K050 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K051 | SCREW | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K052 | TRAY ASSEMB | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K053 | SPACER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K054 | TRAY ASSEMB | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K056 | FLOODLIGHT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K057 | L-BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K059 | SPEAKER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K05944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K060 | ANTENNA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001K06044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K201 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83050376 | -1 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971200 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971265 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 5/15/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K208 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039973 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD: 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971264 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82971262 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K216 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971261 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K219 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971260 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971258 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K221 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K224 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971254 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K225 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971253 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K227 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K228 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971252 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K229 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971251 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K231 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K232 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K233 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K240 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Working with buyer to bring in parts. ECD : 5/15/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K241 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD: 5/8/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K242 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971205 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K243 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K246 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971207 | -1 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K247 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971212 | -1 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K248 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K249 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971213 | -1 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K24944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K250 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971227 | -1 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K251 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0625 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K252 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K253 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0676 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K254 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0675 | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K255 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971228 | -1 | Tim Farmer | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K256 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0560 | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K258 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971271 | -1 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K259 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971270 | -1 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K25944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K260 | ANTENNA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82971266 | -1 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001K26044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L002 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L003 | CS AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L004 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L005 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L006 | HAND MICROP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L007 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 200-8686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L008 | PCMCIA MEMO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-10101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L009 | DIPLEXER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L00944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L010 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L011 | HIGH PWR RE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L012 | BLANKET UNI | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L013 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L014 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L015 | SATELLITE D | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L016 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L017 | SPLITTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L018 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L01844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L020 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L021 | ANTENNA ASS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L022 | PLUGS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L023 | CIR BREAKER | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82967974 | -1 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L024 | PUBLIC AD A | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L025 | PILOT CONTR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L026 | COPILOT CON | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L027 | SPLINE | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 3/14/2019 / CVA0197 | 1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L028 | CNI-SP COUN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L029 | DIITAL SWIT | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83027027 | -1 |  | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L02944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L030 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031417 | -1 |  | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L031 | VHF DTAT RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L032 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-3030RF0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L033 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L034 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L035 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L036 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L037 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L038 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L039 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L03944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L040 | SCREW | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L041 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L042 | SPACER | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 3/14/2019 / CVA0184 | 1 | Tim Farmer | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L043 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L044 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L045 | FLOODLIGHT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L046 | GPS.WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L047 | SPEAKER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L048 | ANTENNA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | VFH10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001L04844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/14/2020 / CVA0544 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L213 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/9/2020 / CVA0671 | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83051349 | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83051348 | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Working with buyer to bring in parts; ECD: 6/30/2020 | -2 |  | Mary Kathleen Chaney |  | 698286-105 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L219 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/29/2020 | -2 |  | Mary Kathleen Chaney |  | 698286-205 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001L22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0630 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M204 | PAPRE-AMP | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0632 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M205 | HAND MICROP | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M206 | DIGITAL SWI | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955972 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0634 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M208 | COMPACT FLA | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604373-016 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M209 | COMBINER RF | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M210 | TX COUPLER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020/ CVA0705 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M211 | PANEL ASSEM | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3351980-53 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M212 | CONTROL PAN | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 3365866-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82955983 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M214 | HIGH POWER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/11/2020 / CVA0699 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M215 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0707 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M216 | SATELLITE D | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0702 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M217 | COUPLER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955988 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M218 | SPLITTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0698 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M219 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/22/2020 / CVA0701 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0700 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M221 | ETHERNET | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M222 | PRINTER | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M223 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DOs 82974394, 83022241 and 83021963 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M224 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M225 | PMD DUST CO | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82918419 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M226 | PANEL ASSEM | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD: 5/15/2020 | -7 | Tim Farmer | Mary Kathleen Chaney |  | 697906-21 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M227 | PANEL ASSEM | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -7 | Tim Farmer | Mary Kathleen Chaney |  | 697906-23 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M228 | HUD ELECT U | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 6/15/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 697940-19 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -6 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M230 | PILOT CONTR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M231 | COPILOT CON | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M233 | MISSION DIS | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M234 | VIDEO SWITC | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M235 | DIGITAL SW | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD: 5/15/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M236 | DIGITAL CRE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD: 5/15/2020 | -13 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M237 | VHF DATA RA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0636 CVA0637 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M238 | FLOODLIGHT | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M239 | L-BAND ANTE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M24044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M241 | SPEAKER | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M24144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M242 | ANTENNA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0713 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001M24244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82956015 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604373-016 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 5/8/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0714 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/9/2020 / CVA0716 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0709 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0710 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N213 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 5/8/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N221 | DIGITAL CRE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -5 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0565 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N226 | ANTENNA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/22/2020 / CVA0706 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001N22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -1 |  | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P203 | HIGH POWER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82957945 | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82957943 | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0711 | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0787 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD: 5/15/2020 | -3 |  | Mary Kathleen Chaney |  | 697906-21 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD : 6/2020 | -3 |  | Mary Kathleen Chaney |  | 697906-23 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -3 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -3 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -4 |  | Mary Kathleen Chaney |  | 698286-105 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -8 |  | Mary Kathleen Chaney |  | 698286-205 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P219 | GPS/WAAS AN | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001P21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R202 | PIN, CONTRA | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R203 | EMU | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82976599 | -1 |  | Mary Kathleen Chaney |  | 3361873-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82976575 | -1 |  | Mary Kathleen Chaney |  | 3365774-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82976588 | -1 |  | Mary Kathleen Chaney |  | 3365776-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3366233-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R214 | BACKSHELL | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R216 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 650HS010NF09 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R219 | ADAPTER HUB | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0502 | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 |  | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0503 | 0 |  | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R227 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R228 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R231 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LS35301B06AY | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R233 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | M83536-16-022M | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MS21042-04 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R235 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82901608 | 0 |  | Mary Kathleen Chaney |  | MS21042-06 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MS35206-245 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS1149DN832H | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS600-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS601-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001R23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S202 | PIN, CONTRA | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0562 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0564 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3361873-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S208 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365774-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365776-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3366233-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82852839 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S217 | ETHERNET | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 650HS010NF09 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S219 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S221 | ADAPTER HUB | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82852851 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S222 | CNI-SP COUN | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S227 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S228 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S231 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S233 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LS35301B06AY | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | M83536-16-022M | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0563 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS21042-04 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0558 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS21042-06 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS35206-245 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS1149DN832H | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS600-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S24044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S241 | SCREW | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS601-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001S24144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0760 | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0767 | 0 |  | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0665 | 0 |  | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0666 | 0 |  | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0667 | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973325 | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82978401 | -1 |  | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973294 | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973298 | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973300 | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973302 | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD : 6/20 | -1 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039952 | -1 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039955 | -1 |  | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0608 | 0 |  | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0763 | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T221 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0654 | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T227 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82934132 and 83021951 | 0 |  | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T228 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD : 6/2020 | -1 |  | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T229 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82973257 | 0 |  | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T22944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0663 | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T231 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0776 | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T233 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T234 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0756 | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0662 | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T23944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T241 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0650 | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T242 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted by DCMA on 4/3/2020 / CVA0757 | 0 |  | Mary Kathleen Chaney |  | 698286-107 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T243 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0758 | 0 |  | Mary Kathleen Chaney |  | 698286-207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0759 | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0651 | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T246 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T247 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T248 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0657 | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T249 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T24944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T250 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0660 | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T251 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T252 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0658 | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T253 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0664 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T254 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0689 | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T255 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0646 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T256 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0648 | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0691 | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T258 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T259 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0652 | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T25944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T260 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T26044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T261 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T26144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T262 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/28/2020 / CVA0768 | 0 |  | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001T26244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U201 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031860 | 0 |  | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031861 | -12 |  | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U203 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83031862 | -3 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO U204 | -1 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/28/2020 / CVA0796 | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82959705 | 0 |  | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3366233-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031909 | -2 |  | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0708 | 0 |  | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031961 | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -2 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 698266-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031978 | -1 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 |  | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U21944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031981 | -2 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22044036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U221 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031983 | -2 |  | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U222 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031987 | -1 |  | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U224 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031988 | -1 |  | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U225 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031994 | -1 |  | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U226 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031995 | -2 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22644036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U227 | KIT | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001U22744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V201 | GPS/WAAS | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V202 | PA PRE-AMP | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955997 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V203 | PUBLIC ADRE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -2 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V204 | PILOT CONTR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V205 | COPILOT CON | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V208 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V209 | SPEAKER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955995 | -2 | Tim Farmer | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001V20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0672 | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20144036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0674 | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20244036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | At risk; pending mod to the PoP | -1 |  | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20344036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20444036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20544036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698286-107 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20744036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0678 | 0 |  | Mary Kathleen Chaney |  | 698286-207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20844036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0673 | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001X20944036
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7012 | C130 | AOA | FA8625-18-F-7012 |  | 2001 | AIRCRAFT | 2020-08-31 |  | James B Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5900 | -1 |  | Mariah Callins |  |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7012200144074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1002AA | SEE CLIN | 2020-07-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-07-01 |  | FA8625-18-F-70141002AA44013
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-06-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-06-01 |  | FA8625-18-F-70141003AA43983
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-07-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-07-01 |  | FA8625-18-F-70141003AA44013
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-08-03 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-03 |  | FA8625-18-F-70141003AA44046
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4006 | OVER & ABOV |  |  | Jim Porter | AT RISK |  |  |  | Tim Farmer | Mariah Callins | OVER AND ABOVE (O&A) - INSTALLS |  | 1 | 1 | U | 2020-06-30 | 2020-06-30 | FA8625-18-F-70194006
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | B015 | SPARE CIVIL | 2020-06-30 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | DO's 83001433 & 83001434 have been submitted to LM QA to be presented to DCMA for acceptance | 0 | Daniel L Kiefer | Mariah Callins |  | 100-601967-113 | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7019B01544012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | C001 | 100-601967- | 2020-08-31 |  | Jim Porter | AT RISK |  |  | 0 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019C00144074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | C003 | S67-1575-13 | 2020-08-31 |  | Jim Porter | AT RISK |  |  | 0 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019C00344074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D001 | ADS-B OUT N | 2020-08-31 |  | Jim Porter | AT RISK |  |  | -1 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019D00144074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D002 | HC/MC-130J | 2020-08-31 |  | Jim Porter |  |  |  | 0 |  | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019D00244074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D003 | C-130J ADS- | 2020-08-31 |  | Jim Porter |  |  |  | 0 |  | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019D00344074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D004 | C-130J ADS- | 2020-08-31 |  | Jim Porter | AT RISK |  |  | -1 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019D00444074
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1003 | MC-130J SEV | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to plan. | -1 | Mark P Lewandowski | Brittany N Scott | MC-130J SEVEN INC 1-2 AND LAIRCM GROUP A INSTALLS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7162100344012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1004 | MC-130J SEV | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to plan. | -1 | Mark P Lewandowski | Brittany N Scott | MC-130J SEVEN LAIRCM GROUP B INSTALLS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7162100444012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1005 | ADS-B OUT I | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to plan. | -1 | Mark P Lewandowski | Brittany N Scott | ADS-B OUT INC 1-2 (INSTALL ADS-B OUT DURING INC 1-2 CONFIGURATION) |  | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7162100544012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4001 | MC-130J INC | 2020-07-31 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final Inc 1-2 Aircraft expected to deliver in June. O&A to be closed out by July. | -1 | Mark P Lewandowski | Brittany N Scott | MC-130J INC1-2 OVER AND ABOVE CARE & MAINTENANCE |  | 1 | 1 | U | 2020-07-31 |  | FA8625-18-F-7162400144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4001AD | MAINTENANCE |  |  | Jackie L Macedonia | AT RISK | System/Database Disconnects within LM Systems | No CLIN 4001AD on contract. LM believes this line item is on the OTD list in error. |  |  | Brittany N Scott |  |  | 1 | 1 | U | 2020-07-31 | 2020-07-31 | FA8625-18-F-71624001AD
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4002 | MC-130J SIX | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to plan. | -1 | Mark P Lewandowski | Brittany N Scott | MC-130J SIX INC 1-2 LSPR/CIUR INSTALLS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7162400244012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 5001 | ADS-B OUT/O | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | 5863 tracking to plan. | -1 |  | Brittany N Scott | ADS-B OUT/OPTION X INSTALL ON 16-5863 |  | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7162500144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | 1005 | CEVA AND LL | 2020-06-30 | 2022-06-30 | Brian D Ginn | AT RISK | Contract Modification Expected to Change PoP Date | PoP extension requested | -1 |  | Jordan R Smythe | RAAF LONG LEAD ITEMS CEVA AND ITEM MANAGEMENT |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401100544012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A001 | BLANKING UN | 2020-06-20 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83023673; PN 357048-001 / SO 10069076 | -2 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 357048-001 | 1 | 1 | J | 2020-06-20 |  | FA8625-18-F-7401A00144002
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A002 | PILOT ABY | 2020-06-20 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83024043; PN 698261-1 / SO 10069075 | -5 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 698261-1 | 1 | 1 | J | 2020-06-20 |  | FA8625-18-F-7401A00244002
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A003 | COPILOT | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83024186; PN 698261-2 / SO 10069074 | -5 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 698261-2 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401A00344012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C001 | SPEAKER | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025870; PN 12890 / SO 10069073 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 12890 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C002 | CARGO AREA | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025875; PN 12891 / SO 10069072 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 12891 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00244012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C003 | PRINTER | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025880; PN 42820325 / SO 10069071 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 42820325 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00344012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C004 | FAN | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025898; PN 645055-3 / SO 10069070 | -3 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 645055-3 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00444012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C005 | PANEL ABY | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83023684; PN 697906-21 / SO 10069069 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697906-21 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00544012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C006 | PANEL ABY | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83023691; PN 697906-23 / SO 10069068 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697906.23 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00644012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C007 | HUD ELECTRO | 2020-06-30 |  | Brian D Ginn | AT RISK |  |  | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697940.21 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00744012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C008 | DIGITAL SWI | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83023740; PN 698286-103 / SO 10069066 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 698286-103 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00844012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C009 | DIGTAL CREW | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025911 & 83026248; PN 698286-203 / SO 10069065 | -3 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 698286-203 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00944012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C00A | VHF DATA RA | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025915; PN 965-1696-081 / SO 10069064 | -2 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 965-1696-081 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00A44012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C00B | FLOODLIGHT | 2020-06-30 | 2020-06-05 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83025919; PN S2491-101 / SO 10069063 | -2 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | S2491-101 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401C00B44012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | D001 | PROCESSOR | 2020-06-30 |  | Brian D Ginn | AT RISK | Supplier Capacity | At risk; P-coded part; P/N 698266-1 / SO 10069102 (2 each) | -2 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS: EXHIBIT D - SPECIAL MISSION DISPLAY PROCESSOR | 698266-1 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401D00144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | 1001 | CEVA & ITEM | 2020-07-31 |  | Cindy Failor | AT RISK | Other | CLIN for CEVA/IA tied to open deliverable CLINs. Cannot DD250 until all other CLINs are delivered. | -1 |  | Olivia M Haller | FMS ISAREL SPARES CEVA AND ITEM MANAGEMENT |  | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801100144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A001 | ICE DETECTO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 0871HM3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A002 | ANTENNA STA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 10-259.10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A003 | INSULATION | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 10-388527-422 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A004 | SIGNAL COND | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 1221AU1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A005 | MATTRESS AS | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 19260005 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A006 | LINK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 23058078 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A007 | FILTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 23061825 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A008 | NOZZLE ASSY | 2020-07-31 |  | Cindy Failor |  |  |  | 0 |  | Olivia M Haller |  | 23089482 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A009 | COMPUTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 27801-01-03 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A00944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A010 | CIRCUIT BRE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 2TC14-2.5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A011 | MICROWAVE O | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 300-1834-01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A012 | ETAC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 304820-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A013 | AUX VENT VA | 2020-07-31 |  | Cindy Failor | AT RISK | DD250 Accepted In WAWF | DD250 accepted on 2/11, LM coordinating with DCMA to investigate recycling of ELIN. | 0 |  | Olivia M Haller |  | 3291272-2-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A014 | DUCK ASM | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3311278-81 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A015 | CUR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3328558-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A016 | CUR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3328558-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A017 | LCK ASSY C | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338700-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A018 | LCK ASSY C | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338700-6 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A019 | TOWPLATE AS | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338784-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A01944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A020 | LOCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338863-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A021 | LOCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338863-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A022 | SAFETY WALK | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338999-53 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A023 | SAFETY WALK | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338999-54 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A024 | FIRE EXTING | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3341006-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A025 | FLOOR COVER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3351171-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A026 | TUBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3351615-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A027 | ICS CORD | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352003-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A028 | BRACKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352180-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A029 | CARRIER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352181-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A02944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A030 | BRACKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352181-2 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A031 | STRAP ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3353439-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A032 | RAIL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3355574-8 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A033 | TANK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3357570-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A034 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3357761-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A035 | TUBE ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3358516-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A036 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3365895-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A037 | PANEL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3365986-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A038 | RUB STRIP | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 338262-2 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A039 | RUB STRIP | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 338262-4 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A03944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A040 | POS INDICAT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 364260-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A041 | TUBE ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 370741-884 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A042 | TUBE ASM | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 371352-341 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A043 | BOOSTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 374461-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A044 | CABLE ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 374943-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A045 | CABLE ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  | Pending PCOL. Working to Contract Dates - On Time DD250 Submittal Expected | -10 |  | Olivia M Haller |  | 376765-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A046 | LEG ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 382990-13 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A047 | TUBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 382990-17 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A048 | VALVE, EJEC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3D3556-01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A049 | VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 5145-00-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A04944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A050 | RECEPTACLE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 5256M4 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A051 | LIFE RAFT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 63880-103 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A052 | LIFE RAFT | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -2 |  | Olivia M Haller |  | 63880-104 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A053 | GEARBOX | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 695700-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A054 | WINCH | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 695755-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A055 | CONTROL UNI | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697856-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A056 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697906-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A057 | RADAR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697908-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A058 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697910-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A059 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697911-17 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A05944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A060 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697913-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A061 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697915-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A062 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697919-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A063 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697921-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A064 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697922-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A065 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697923-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A066 | PANEL ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697925-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A067 | PANEL ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697930-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A068 | PNL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697936-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A069 | PANEL | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -1 |  | Olivia M Haller |  | 697939-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A06944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A070 | TRAY MOUNT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697940-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A071 | BREAKER UN | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | 0 |  | Olivia M Haller |  | 697941-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A072 | POWER SPLY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697942-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A073 | CONTROLLER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697967-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A074 | COMPUTER | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697960-9 | -1 |  | Olivia M Haller |  | 697960-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A075 | PUBLIC ADRE | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697966-301 | -1 |  | Olivia M Haller |  | 697968-301 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A076 | GRIP ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697976-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A077 | MFCD | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697977-21 | -2 |  | Olivia M Haller |  | 697977-21 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A078 | FUEL MGT | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697980-1 | -1 |  | Olivia M Haller |  | 697980-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A079 | FIRESHIELD | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697985-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A07944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A080 | SEAL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697988-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A081 | VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697966-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A082 | CHECK VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697998-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A083 | PNUEMATIC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697999-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A084 | FIRE CONTRO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698009-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A085 | NACELLE INT | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -1 |  | Olivia M Haller |  | 698015-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A086 | PANEL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698024-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A087 | DUAL SLOT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698089-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A088 | COMPRESSOR | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698269-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A089 | DUCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698269-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A08944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A090 | WATER WASH | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698270-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A091 | FILTER | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; potential late delivery. | 0 |  | Olivia M Haller |  | 808574-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A092 | POWER SPLY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 8ES003417-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09244043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A093 | INDICATO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 95-42-11S6-70397 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A094 | SPHERE | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -3 |  | Olivia M Haller |  | A802400-10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A095 | TEST PROBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | ABC56103-B-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A096 | FILTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | AC2291EB10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A097 | AIR DATA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | ADA130J723 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A098 | PLUG FLARED | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | AS5168VV08 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A09844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A100 | FILTER | 2020-07-31 |  | Cindy Failor | ON TIME | DD250 Accepted In WAWF | Working to Contract Dates - On Time DD250 Submittal Expected | 0 |  | Olivia M Haller |  | D9-155-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A101 | THERMOCOUPL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | HMCL150/P1/5K | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A103 | PLUG | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA6T25W8SCL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A104 | PLUG | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA6T25W8SEL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A105 | RECEPTACLE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA7T21W75PAL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10544043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A106 | ANTENNA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LG81CE01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10644043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A107 | TERMINAL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS35076-3-03 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10744043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A108 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS35310B02AY | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10844043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A109 | WASHER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS5984D08M | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A10944043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A110 | PIN | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | NAS1366S7S11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A11044043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A111 | SINGAL COND | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | NCAL52K0/500F | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A11144043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A113 | RESISTOR | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | RNC65H1003FRF | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A11344043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A114 | GASKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | SG278000-02 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801A11444043
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7803 | C130 | AOA | FA8625-18-F-7803 |  | 1001 | CEVA & ITEM | 2020-06-30 |  | Cynthia C Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track- CLIN 1000 complete, preparing CoC | 0 |  | Olivia M Haller | FMS ISRAEL SPARES CEVA AND ITEM MANAGEMENT |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7803100144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7803 | C130 | AOA | FA8625-18-F-7803 |  | A001 | LPCR RTP MO | 2020-06-30 |  | Cynthia C Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track | 0 |  | Olivia M Haller |  | 780R164G03 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7803A00144012
ALX | Other | FA8625-16-D-6458 | FA8625-18-F-7803 | C130 | AOA | FA8625-18-F-7803 |  | A002 | OIL COOLER | 2020-06-30 |  | Cynthia C Failor |  |  |  | 0 |  | Olivia M Haller |  | 695807-7 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7803A00244012
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0004 | PHYSICAL CO |  |  | Jim Porter | AT RISK |  |  |  |  | Mary Kate Chaney | PHYSICAL CONFIGURATION AUDIT |  | 1 | 1 | U | 2020-08-10 | 2020-08-10 | FA8625-19-F-70330004
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0005 | INVENTORY C |  | 2020-05-29 | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | ICP Support Services, CoC to close out last day of PoP |  |  | Mary Kate Chaney | INVENTORY CONTROL POINT (ICP) SUPPORT |  | 1 | 1 | U | 2020-05-29 | 2020-05-29 | FA8625-19-F-70330005
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-06-08 |  | Jim Porter | AT RISK |  |  | 0 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-06-08 |  | FA8625-19-F-7033000843990
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-07-07 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-07-07 |  | FA8625-19-F-7033000844019
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-08-03 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-08-03 |  | FA8625-19-F-7033000844046
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-06-08 |  | Jim Porter | AT RISK |  |  | 0 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-06-08 |  | FA8625-19-F-7033000943990
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-07-07 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-07-07 |  | FA8625-19-F-7033000944019
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-08-03 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | U | 2020-08-03 |  | FA8625-19-F-7033000944046
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4010 | CONTRACTOR | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK |  |  | -5 |  | Reda R Belmaachi | CONTRACTOR MAINTENANCE TEAM |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905401044074
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4020 | LOGISTICS S | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK |  |  | -5 |  | Reda R Belmaachi | LOGISTICS SUPPORT REPRESENTATIVE |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905402044074
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4030 | REPAIR OF R |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | REPAIR OF REPAIRABLES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-79054030
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4040 | INTEGRATED | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK |  |  | -5 |  | Reda R Belmaachi | INTEGRATED LOGISTICS SUPPORT |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905404044074
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4050 | CONSUMABLE |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | CONSUMABLE REPLENISHMENT SPARES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-79054050
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4060 | ENGINEERING | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK |  |  | -5 |  | Reda R Belmaachi | ENGINEERING TECHNICAL SUPPORT |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905406044074
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4070 | PUBLICATION |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | PUBLICATION UPDATES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-79054070
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4080AA | NOUN |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | VALUE ADDED TAX - CONTRACTOR MAINTENANCE TEAM |  | 1 | 1 | U | 2020-08-30 | 2020-08-30 | FA8625-19-F-79054080AA
ALX | Other | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4080AB | NOUN |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | VALUE ADDED TAX - LOGISTICS SUPPORT REPRESENTATIVE |  | 1 | 1 | U | 2020-08-30 | 2020-08-30 | FA8625-19-F-79054080AB
ALX | Other | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B001 | CREW SEAT A | 2020-06-30 | 2020-04-30 | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0005) on 4/21/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 3A067-0010-02 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169B00144012
ALX | Other | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B002 | BELT,SAFETY | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0004) on 1/13/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 54H19651 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169B00244012
ALX | Other | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B003 | HARNESS | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0002) on 1/13/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 57D677 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169B00344012
ALX | Other | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B004 | 12'SEAT RAC | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0003) on 11/22/19 and parts shipped | 0 |  | Brittany N Scott |  | LS5301 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169B00444012
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0106AA | LAIRCM-ATW | 2020-05-12 |  | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Kit was submitted to DCMA 08/2019; Kit was delivered to Customer 10/2019; Working with DCMA to close item and identify issue with CLIN still being open in MOCAS. | 0 | Daniel L Kiefer | Reda R Belmaachi | LAIRCM-ATW A-KIT BENCH STOCK KIT |  | 1 | 1 | J | 2020-05-12 |  | N00019-17-C-00610106AA43963
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0106AB | LAIRCM-ATW | 2020-05-12 |  | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track. | -1 | Daniel L Kiefer | Reda R Belmaachi | LAIRCM-ATW A-KIT BENCH STOCK KIT |  | 1 | 1 | J | 2020-05-12 |  | N00019-17-C-00610106AB43963
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AB | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  | Kit accepted to W09 - Bonded Storage on 9/27/2019 | 0 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-00610208AB44042
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AC | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  |  | 0 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-00610208AC44042
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AD | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  |  | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-00610208AD44042
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AE | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  |  | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-00610208AE44042
ALT | Other | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AF | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  |  | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-00610208AF44042
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AB | EMU | 2020-06-01 | 2020-03-16 | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82859098 / CVA0030 pending DCMA acceptance in WAWF; PN 100-601978-401 / SO 10108634 | 0 | Philip C Bailey | Reda R Belmaachi | ELECTRONIC MODULE, STANDARDIZED P/N 100-601978-401 |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AB43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AC | PMD | 2020-06-01 | 2020-06-01 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83050069; PN 100-604003-054 / SO 10108633 | -3 | Philip C Bailey | Reda R Belmaachi | DISPLAY UNIT, FLIGHT INFORMATION |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AC43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AF | HAND MICROP | 2020-06-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | MICROPHONE, DYNAMIC |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AF43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AG | DIGITAL SWI | 2020-06-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | DIGITAL SWITCHING UNIT |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AG43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AH | PMD TETHER | 2020-06-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | CABLE ASSEMBLY, SPECIAL PURPOSE, ELECTRICAL |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AH43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AM | PANEL ASSY | 2020-06-01 | 2020-06-01 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; 2ea DO 83054231, 2ea DO 83056044; PN 3365972-1 / SO 10108624 | -4 | Philip C Bailey | Reda R Belmaachi | PANEL, INDICATOR |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AM43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AN | PRG INT BLA | 2020-08-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | BLANKING UNIT |  | 1 | 1 | J | 2020-08-01 |  | N00019-19-F-41930005AN44044
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AX | ETHERNET SW | 2020-05-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | SWITCH, ELECTRONIC |  | 1 | 1 | J | 2020-05-01 |  | N00019-19-F-41930005AX43952
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AY | PRINTER | 2020-05-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | PRINTER, AUTOMATIC DATA PROCESSING |  | 1 | 1 | J | 2020-05-01 |  | N00019-19-F-41930005AY43952
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AZ | ANTENNA AS | 2020-06-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | ANTENNA ASSY |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005AZ43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BA | HUD ELECTRO | 2020-06-01 |  | Nick Kljucaric | AT RISK | Other | At risk; HUD -- P-coded; PN 697940-25 / SO 10108611 | -4 | Philip C Bailey | Reda R Belmaachi | ELECTRONIC COMPONENTS ASSEMBLY |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-41930005BA43983
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BJ | FLOODLIGHT | 2020-05-01 |  | Nick Kljucaric | AT RISK |  |  | 0 | Philip C Bailey | Reda R Belmaachi | FLOODLIGHT, ELECTRIC |  | 1 | 1 | J | 2020-05-01 |  | N00019-19-F-41930005BJ43952
ALT | Other | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BS | PANEL ASM | 2020-05-01 | 2020-04-22 | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 83032007; PN 3365867-1 / SO 10108595 | 0 | Philip C Bailey | Reda R Belmaachi | PANEL ASSEMBLY |  | 1 | 1 | J | 2020-05-01 |  | N00019-19-F-41930005BS43952
ALA | Other | N00383-19-F-Q50L |  | C130 | AOI | N00383-19-F-Q50L |  | 0005AA | UPPER BUNK | 2020-07-02 | 2020-07-02 | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 82973504; PN 3353181-5 / SO 10107891 | -1 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-07-02 |  | N00383-19-F-Q50L0005AA44014
ALA | Other | N00383-19-F-Q50M |  | C130 | AOI | N00383-19-F-Q50M |  | 0001AA | CLEVIS ASSY | 2020-05-12 | 2020-04-14 | Nicholas J Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82942999; PN 3355867-1 / SO 10107714 | 0 |  | Reda R Belmaachi |  | 3355867-1 | 1 | 1 | J | 2020-05-12 |  | N00383-19-F-Q50M0001AA43963
ALL | Other | N00383-19-P-D125 |  | C130 | AOI | N00383-19-P-D125 |  | 0001AA | INTERFACE U | 2020-08-06 |  | Nicholas J Kljucaric | AT RISK |  |  | -4 | Philip C Bailey | Reda R Belmaachi | EVALUATE, REPAIR AND/OR MODIFY P/N 698258-7 |  | 1 | 5 | J | 2020-08-06 |  | N00383-19-P-D1250001AA44049
ALA | Other | N00383-20-F-Q503 |  | C130 | AOI | N00383-20-F-Q503 |  | 0004AA | FITTING, ST | 2020-08-24 |  | Nick Kljucaric | ON TIME |  | PN 3351230-21 / SO 10109808 | -1 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-08-24 |  | N00383-20-F-Q5030004AA44067
ALA | Other | N00383-20-F-Q503 |  | C130 | AOI | N00383-20-F-Q503 |  | 0006AA | SEAT COVER | 2020-07-24 | 2020-07-24 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83032368, PN 1A067-0125CS / SO 10109811 | 0 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-07-24 |  | N00383-20-F-Q5030006AA44036
ALA | Other | N00383-20-F-Q505 |  | C130 | AOI | N00383-20-F-Q505 |  | 0001AA | COUPLER NET | 2020-08-26 |  | Nick Kljucaric | ON TIME |  | PN LN72000-18 / SO 10110366 | -1 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-08-26 |  | N00383-20-F-Q5050001AA44069
ALL | Other | N00383-20-P-D009 |  | C130 | AOI | N00383-20-P-D009 |  | 0001AB | CONTROL, CO | 2020-05-05 | 2020-05-05 |  | AT RISK | Contract Mod Requested | At risk; awaiting contract mod to reduce CLIN qty to 5ea; NFF repairs | 0 | Philip C Bailey | Reda R Belmaachi | NFF CNI-MU |  | 1 | 5 | J | 2020-05-05 |  | N00383-20-P-D0090001AB43956
ALL | Other | N00383-20-P-D010 |  | C130 | AOI | N00383-20-P-D010 |  | 0001AB | CONTROL,COM | 2020-05-05 | 2020-04-14 |  | ON TIME | DD250 Accepted In WAWF | Closed; NFF repairs | 0 | Audrey L Clark | Reda R Belmaachi | NFF CNI-MU |  | 1 | 5 | J | 2020-05-05 |  | N00383-20-P-D0100001AB43956
PAY | Other | N00421-18-P-0132 |  | C130 | AOF | N00421-18-P-0132 |  | 0001 | DRIVE ASSMB | 2020-06-16 | 2020-06-16 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83062131; PN 3350371-5 / SO 10105955 | -1 |  | Reda R Belmaachi | SERVO DRIVE ASSEMBLY P/N 3350371-5 |  | 1 | 1 | J | 2020-06-16 |  | N00421-18-P-0132000143998
PAY | Other | N00421-18-P-0132 |  | C130 | AOF | N00421-18-P-0132 |  | 0002 | DRIVE ASSMB | 2020-06-16 | 2020-03-12 | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82858098 / CVA0002; PN 3350372-3 / SO 10105956 | 0 |  | Reda R Belmaachi | SERVO DRIVE ASSEMBLY P/N 3350372-3 |  | 1 | 1 | J | 2020-06-16 |  | N00421-18-P-0132000243998
PAY | Other | N00421-18-P-0132 |  | C130 | AOF | N00421-18-P-0132 |  | 0003 | DRIVE ASSMB | 2020-06-16 |  | Nick Kljucaric | AT RISK |  |  | 0 |  | Reda R Belmaachi | SERVO DRIVE ASSEMBLY P/N 3350370-3 |  | 1 | 1 | J | 2020-06-16 |  | N00421-18-P-0132000343998
ALA | Other | SPE4A5-19-F-09L6 |  |  | AOI | SPE4A5-19-F-09L6 |  | 0001 | TUBE,BENT,M | 2020-08-07 |  | Nicholas J Kljucaric | AT RISK |  |  | -13 | Audrey L Clark | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-07 |  | SPE4A5-19-F-09L6000144050
ALA | Other | SPE4A5-19-F-192D |  |  | AOI | SPE4A5-19-F-192D |  | 0001 | STRIP,TRAIL | 2020-05-25 | 2020-05-25 | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; 2ea DO 83026369, 6ea DO 83026323, 1ea PO ECD 05/01/2020; PN 3351252-1 / SO 10105697 | -7 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-05-25 |  | SPE4A5-19-F-192D000143976
ALA | Other | SPE4A5-19-F-202B |  |  | AOI | SPE4A5-19-F-202B |  | 0001 | DUCT ASSEMB | 2020-07-27 | 2020-07-27 | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; 2ea DO 82938378, 1ea DO 82938396; PN 698269-25 / SO 10105696 | -2 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-07-27 |  | SPE4A5-19-F-202B000144039
ALA | Other | SPE4A5-19-F-900X |  |  | AOI | SPE4A5-19-F-900X |  | 0001 | TUBE,BENT,M | 2020-06-30 | 2020-06-30 | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; PO 6535087226 ECD 5/31/20; PN 3354434-1 / SO 10107795 | -24 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-06-30 |  | SPE4A5-19-F-900X000144012
ALA | Other | SPE4A5-19-F-904P |  |  | AOI | SPE4A5-19-F-904P |  | 0001 | TUBE,BENT,M | 2020-08-17 |  | Nicholas J Kljucaric | AT RISK |  |  | -4 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-17 |  | SPE4A5-19-F-904P000144060
ALA | Other | SPE4A5-20-F-3953 |  | C130 | AOI | SPE4A5-20-F-3953 |  | 0001 | BOX,SHIPPIN | 2020-07-09 | 2020-05-31 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 82980890; PN 3354968-1 / SO 10109306 | -476 | Audrey L Clark |  |  |  | 1 | 1 | J | 2020-07-09 |  | SPE4A5-20-F-3953000144021
ALA | Other | SPE4A5-20-F-6636 |  | C130 | AOI | SPE4A5-20-F-6636 |  | 0001 | BAG,ENGINE | 2020-07-21 | 2020-07-21 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; assets STOing to L12; PN ATL1175-001G / SO 10109851 | -11 | Audrey L Clark |  |  |  | 1 | 1 | J | 2020-07-21 |  | SPE4A5-20-F-6636000144033
ALA | Other | SPE4A7-20-F-0083 |  | C130 | AOF | SPE4A7-20-F-0083 |  | 0001 | INSULATION | 2020-08-31 | 2020-05-30 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 82891611 / CVA0002Z; PN 10-388527-400 / SO 10108697 | 7 | Audrey L Clark |  |  | 98897 10-388527-400 | 1 | 1 | J | 2020-08-31 |  | SPE4A7-20-F-0083000144074
ALA | Other | SPRPA1-19-F-Q504 |  |  | AOI | SPRPA1-19-F-Q504 |  | 0001AA | FLAP ASSY | 2020-08-06 |  | Nicholas J Kljucaric | AT RISK |  |  | -1 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-06 |  | SPRPA1-19-F-Q5040001AA44049