## AMMM OTD 306090
MCS ACO Code | ECS LOB | Contract Number | Delivery Order | GK Platform | MCS ISP Code | MCS PIIN | MCS SPIIN | MCS Line Item ID | MCS Noun | MCS Delivery Schedule Date | WB ECD | GK CLIN Program Manager | High-Level Delivery Status | WB Status | WB Comments | MCS Bal Qty Shed | WB CLIN Status POC | GK LM Contracts POC | ECS CLIN Description | MCS Part Number | MCS Current Status | MCS Contract Purpose | MCS Contract Type | MOCAS Delivery Due Date | MCS Service Completion Date | concat
ALG | AMMM | FA8504-16-D-0001 | FA8504-19-F-0050 | C130 | AOI | FA8504-19-F-0050 |  | 3006AA | ADDITIONAL | 2020-09-30 |  | Avery D Jones | AT RISK |  |  | -1 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (C-130 PECULLIAR), HOSE ASSEMBLY, PN MS8005N252FA000 |  | 1 | 1 | J | 2020-09-30 |  | FA8504-19-F-0050None3006AA2020-09-30 00:00:00
ALG | AMMM | FA8504-16-D-0001 | FA8504-19-F-0052 | C130 | AOI | FA8504-19-F-0052 |  | 3006AM | ADDITIONAL |  |  | Avery D Jones | [6 empty] | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (C-130 PECULLIAR) MODULE, P/N 780R191G02 |  | 1 | 1 | J | 2020-09-30 | 2020-09-30 | FA8504-19-F-0052None3006AMNone
ALG | AMMM | FA8504-16-D-0001 | FA8504-20-F-0018 |  | AOR | FA8504-20-F-0018 |  | 3031 | SERVICE | [9 empty] | PLB1 BEACON REPLACEMENT |  | 1 | 1 | J | 2020-06-29 | 2020-06-29 | FA8504-20-F-0018None3031None
ALG | AMMM | FA8504-16-D-0001 | FA8504-20-F-0018 |  | AOR | FA8504-20-F-0018 |  | 3050 | SERVICE | [9 empty] | PROPOSAL PREPARATION |  | 1 | 1 | J | 2020-06-29 | 2020-06-29 | FA8504-20-F-0018None3050None
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AB | ADDITIONAL | 2020-06-19 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697927-1 / Qty 1 / Sales Order 10069090 / DO 82972116 (CVA0009) Accepted in WAWF 5/6/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-06-19 |  | FA8504-18-F-0050None2006AB2020-06-19 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AE | ADDITIONAL | 2020-08-20 | 2019-12-20 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; DO 82825172 (CVA0002) in WAWF awaiting DCMA acceptance | 0 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 697941-3 | 1 | 1 | J | 2020-08-20 |  | FA8504-18-F-0050None2006AE2020-08-20 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AF | ADDITIONAL | 2020-07-20 | 2020-06-15 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO# 83064295/ processing in shipping | 0 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 3291272-2-3 | 1 | 1 | J | 2020-07-20 |  | FA8504-18-F-0050None2006AF2020-07-20 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0050 | C130 | AOR | FA8504-18-F-0050 |  | 2006AH | ADDITIONAL | 2020-06-19 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697922-5 / Qty 1 / Sales Order 10069095 / DO 82925887 (CVA0007) Accepted in WAWF 3/27/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) | 697922-5 | 1 | 1 | J | 2020-06-19 |  | FA8504-18-F-0050None2006AH2020-06-19 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AC | ADDITIONAL | 2020-08-31 | 2020-06-30 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; P-Coded part. ECD 6/30/2020. PN 63880-104 / SO 10069047..Mod POP extended to 8/31/2020 | -2 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) LIFE RAFT, 46-MAN, PN 63880-104; NSN: 4220-01-483-3204 | 63880-104 | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-0068None2006AC2020-08-31 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AE | ADDITIONAL | 2020-06-01 | 2020-05-13 | Avery D Jones | ON TIME | DD250 Accepted In WAWF | Complete. DO 83056759; Shipment # 805666. Accepted by DCMA; Shipping | 0 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) AUX VENT VALVE, PN 3291272-2-3; NSN: 4810-01-583-9245 | 3291272-2-3 | 1 | 1 | J | 2020-06-01 |  | FA8504-18-F-0068None2006AE2020-06-01 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AF | ADDITIONAL | 2020-07-01 | 2020-10-01 | Eric Hall | AT RISK | Delayed Due to COVID-19 Impacts | Requested delivery extension to Nov 1 2020. Contract modification in progress. Expected delivery to arrive by Oct 1 2020; 2ea delayed due to vendor sub-tier being closed due to COVID-19; Sub-tier is back operating at partial capacity. DO# 82974423/ DO# 83030215 | -3 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) GENERATOR, ENGINE, PN 697970-3; NSN: 2925-01-541-5012 | 697970-3 | 1 | 1 | J | 2020-07-01 |  | FA8504-18-F-0068None2006AF2020-07-01 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AG | ADDITIONAL | 2020-06-01 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697903-3 / Qty 4 / Sales Order 10069087 / DO 82898189 (CVA0011) Accepted in WAWF 03/12/2020, DO 82908828 (CVA0012) Accepted in WAWF on 4/17/2020 / DO 82914633 (CVA0013) Accepted in WAWF on 2/28/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) PANEL ASSEMBLY, PN 697903-3; NSN: 6110-01-447-3148 | 697903-3 | 1 | 1 | J | 2020-06-01 |  | FA8504-18-F-0068None2006AG2020-06-01 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0068 | C130 | AOR | FA8504-18-F-0068 |  | 2006AL | ADDITIONAL | 2020-08-31 | 2020-06-05 | Eric Hall | ON TIME | DD250 Accepted In WAWF | Not on track; P-Coded part. PO 6534855408 due 6/5/2020. PN 63880-103 / SO 10069051..in process of requesting late delivery authorization. / Was accepted in WAWF and approved by DCMA on 12/13/2019 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) LIFE RAFT, 46 MAN, PN 63880-103; NSN: 4220-01-483-3201 | 63880-103 | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-0068None2006AL2020-08-31 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0080 | C130 | AOR | FA8504-18-F-0080 |  | 2006 | ADDITIONAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) FLAP ASSEMBLY, OUTER WING, PN 3352602-1 |  | 1 | 1 | J | 2020-06-30 | 2020-06-30 | FA8504-18-F-0080None2006None
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0081 | C130 | AOR | FA8504-18-F-0081 |  | 2006AC | ADDITIONAL |  |  | Avery D Jones | AT RISK |  |  |  |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT(C-130 PECULLIAR) WING FLAP ASSEMBLY, PN 3352604-1, NSN 1560-01-456-0028VM |  | 1 | 1 | J | 2020-09-30 | 2020-09-30 | FA8504-18-F-0081None2006ACNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0083 | C130 | AOR | FA8504-18-F-0083 |  | 2006AC | EQUIPMENT | 2020-08-31 |  | Eric Hall | AT RISK |  |  | 0 |  | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-0083None2006AC2020-08-31 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0083 | C130 | AOR | FA8504-18-F-0083 |  | 2006AD | EQUIPMENT | 2020-08-31 |  | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; P-Coded part. ECD 6/30/2020. PN 63880-104 / SO 10069054..Mod POP extended to 8/31/2020 | -2 | Marques J Bell | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-08-31 |  | FA8504-18-F-0083None2006AD2020-08-31 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0084 | C130 | AOR | FA8504-18-F-0084 |  | 2006AA | EQUIPMENT | 2020-06-30 | 2020-06-01 | Eric Hall | ON TIME | DD250 Accepted In WAWF | PN 697927-1 / Qty 1 / Sales Order 10069083 / DO 82966300 (CVA0006) Accepted in WAWF on 4/28/2020 | 0 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-06-30 |  | FA8504-18-F-0084None2006AA2020-06-30 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-18-F-0084 | C130 | AOR | FA8504-18-F-0084 |  | 2006AF | EQUIPMENT | 2020-09-30 | 2020-09-01 | Eric Hall | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | PN 697941-3 / Qty 3 / Sales Order 10069079 / DO 83100224 (CVA CVA0008Z) Pending DCMA Acceptance | -3 | Charles D Grant | Alicia N Walker | ADDITIONAL USG PURCHASED SPARES AND SUPPORT EQUIPMENT (AS ORDERED) |  | 1 | 1 | J | 2020-09-30 |  | FA8504-18-F-0084None2006AF2020-09-30 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AA | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E) OF OVER AND ABOVE REPAIRS, C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3352602-2; NOUN: FLAP ASSEMBLY, RT; TAIL NUMBER: 08-5726; S/N: LMG-G71-5726-2; CLAIM NUMBER: 1235LA |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057AANone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AB | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E) OF OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 371578-24; NOUN: AILERON ASSEMBLY, RH; TAIL NUMBER: 12-5756; S/N: LAP0124-5756; CLAIM NUMBER: 1263LA |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057ABNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AC | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 371578-24; NOUN: AILERON ASSEMBLY, RH; S/N: LMG74-4957-106: CLAIM NUMBER: 3197IN |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057ACNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AD | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3352604-2; NOUN: FLAP ASSEMBLY, WING RIGHT; TAIL NUMBER: 08-5726; S/N: LMG-G62-5726-2; CLAIM NUMBER: 1236LA |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057ADNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AE | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3351041-1; NOUN: PANEL ASSEMBLY,OG,TRAIL; TAIL NUMBER: 08-6204; CLAIM NUMBER: 1690NM |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057AENone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AF | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3352604-1; NOUN: WING: FLAP ASSEMBLY; TAIL NUMBER: 13-5772; S/N: LMG-G62-5678-1; CLAIM NUMBER: 0384HL |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057AFNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AG | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3352604-2; NOUN: FLAP ASSEMBLY, WING; TAIL NUMBER: 12-5755; S/N: LMG-G62-5755-2; CLAIM NUMBER: 0838AB |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057AGNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0045 | C130 | AOI | FA8504-19-F-0045 |  | 3057AH | MATERIAL |  |  | Eric Hall | AT RISK |  |  |  |  | Alicia N Walker | TEST, TEAR-DOWN AND EVALUATION (TT&E)-OVER AND ABOVE REPAIR (C-130J PECULIAR AND MISSION SPECIFIC ITEMS). P/N: 3363783-2; NOUN: PANEL, TRAILING EDGE; TAIL NUMBER: 05-3145; S/N: 5569; CLAIM NUMBER: 1265LA |  | 1 | 1 | J | 2020-09-21 | 2020-09-21 | FA8504-19-F-0045None3057AHNone
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0046 | C130 | AOI | FA8504-19-F-0046 |  | 3022 | SUPPORT | 2020-09-23 |  | Avery D Jones | AT RISK |  |  | -5 |  | Alicia N Walker | SUSTAINING ENGINEER SUPPORT (MISSION SPECIFIC) |  | 1 | 1 | J | 2020-09-23 |  | FA8504-19-F-0046None30222020-09-23 00:00:00
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0046 | C130 | AOI | FA8504-19-F-0046 |  | 3049 | TRAVEL |  |  | Avery D Jones | AT RISK |  |  |  |  | Alicia N Walker | TRAVEL AND PER DIEM |  | 1 | 1 | J | 2020-09-23 | 2020-09-23 | FA8504-19-F-0046None3049None
ALK | AMMM | FA8504-16-D-0001 | FA8504-19-F-0046 | C130 | AOI | FA8504-19-F-0046 |  | 3050 | PROPOSAL PR |  |  | Avery D Jones | AT RISK |  |  |  |  | Alicia N Walker | PROPOSAL PREPARATION |  | 1 | 1 | J | 2020-09-24 | 2020-09-24 | FA8504-19-F-0046None3050None
ALK | TBD | FA8504-16-D-0001 | FA8504-19-F-0046 | C130 | AOI | FA8504-19-F-0046 |  | 3023 | SUSTAINING |  |  | Avery D Jones | AT RISK |  |  |  |  | Alicia N Walker |  |  | 1 | 1 | J | 2020-09-24 | 2020-09-24 | FA8504-19-F-0046None3023None
ALA | AMMM | FA8553-19-D-0001 | FA8553-20-F-0002 | C130 | AOI | FA8553-20-F-0002 |  | 0010 | KNOBS | 2020-08-12 |  | Kathleen M Atkins | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Tracking to delivery date | -10 |  | Alicia N Walker | C-130J SPARES KNOBS | GP606-V105 | 1 | 1 | J | 2020-08-12 |  | FA8553-20-F-0002None00102020-08-12 00:00:00
ALA | AMMM | FA8553-19-D-0001 | FA8553-20-F-0012 |  | AOI | FA8553-20-F-0012 |  | 1010AB | [10 empty] | GASKETS | GASKET | 1 | 1 | J | 2020-08-10 | 2020-08-10 | FA8553-20-F-0012None1010ABNone
ALA | AMMM | FA8553-19-D-0001 | FA8553-20-F-0012 |  | AOI | FA8553-20-F-0012 |  | 1010AC | [10 empty] | BUSHING SLEEVES | BUSHING SLEEVE | 1 | 1 | J | 2020-08-31 | 2020-08-31 | FA8553-20-F-0012None1010ACNone
ALV | AMMM | FA8625-14-C-6450 |  | C130 | AOH | FA8625-14-C-6450 |  | 6003 | AF16HC130J | 2020-06-30 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5895 | 0 |  | Mary Kathleen Chaney | FY16 USAF HC-130J |  | 1 | 1 | J | 2020-06-30 |  | FA8625-14-C-6450None60032020-06-30 00:00:00
ALV | AMMM | FA8625-14-C-6450 |  | C130 | AOH | FA8625-14-C-6450 |  | 6006 | MC17KC130J | 2020-07-31 |  | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5896 | 0 |  | Mary Kathleen Chaney | FY17 KC-130J AIRCRAFT |  | 1 | 1 | J | 2020-07-31 |  | FA8625-14-C-6450None60062020-07-31 00:00:00
ALK | AMMM | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0008 | HC-130J INC | 2020-07-31 | 2020-07-30 | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CSO 2.5 Kit | -1 |  | Belinda C Young | HC-130J INC 2.5 CSO STATION KIT & TCTO |  | 1 | 2 | V | 2020-07-31 |  | FA8625-15-D-6591000200082020-07-31 00:00:00
ALK | AMMM | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0009 | HC-130J INC | 2020-07-31 | 2020-07-30 | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CSO 2.5 Installs | -1 |  | Belinda C Young | HHC-130J INC 2.5 CSO STATION TKI AT GSO |  | 1 | 2 | V | 2020-07-31 |  | FA8625-15-D-6591000200092020-07-31 00:00:00
ALK | AMMM | FA8625-15-D-6591 | 0002 | C130 | AOH | FA8625-15-D-6591 | 0002 | 0010 | HC-130J INC | 2020-08-19 | 2020-08-18 | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CSO 2.5 Kit | -1 |  | Belinda C Young | HC-130J INC 2.5 CSO STATION KIT FOR SACU |  | 1 | 2 | V | 2020-08-19 |  | FA8625-15-D-6591000200102020-08-19 00:00:00
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | 2002 |  |  |  | Kathleen M Atkins | AT RISK |  |  |  |  | Alicia N Walker | TCAS INTEROPERABILITY TESTING | TCAS INTEROPERABILITY TES | 1 | 1 | U | 2020-09-30 | 2020-09-30 | FA8625-19-F-3805None2002None
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | C001 | GPS/WAAS | 2020-09-30 |  | Kathleen M Atkins | AT RISK |  |  | 0 |  | Alicia N Walker | GPS/WAAS | 100-601967-113 | 1 | 1 | U | 2020-09-30 |  | FA8625-19-F-3805NoneC0012020-09-30 00:00:00
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | C002 | GASKET | 2020-09-30 |  | Kathleen M Atkins | AT RISK |  |  | -1 |  | Alicia N Walker | GASKET | AG477000-17 | 1 | 1 | U | 2020-09-30 |  | FA8625-19-F-3805NoneC0022020-09-30 00:00:00
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | C003 | GPS/WASS | 2020-09-30 |  | Kathleen M Atkins | AT RISK |  |  | 0 |  | Alicia N Walker | GPS/WAAS ANTENNA | S67-1575-135 | 1 | 1 | U | 2020-09-30 |  | FA8625-19-F-3805NoneC0032020-09-30 00:00:00
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | C004 | CEVA | 2020-09-30 |  | Kathleen M Atkins | AT RISK |  |  | -1 |  | Alicia N Walker | CEVA | CEVA | 1 | 1 | U | 2020-09-30 |  | FA8625-19-F-3805NoneC0042020-09-30 00:00:00
ALK | AMMM | FA8625-15-D-6591 | FA8625-19-F-3805 | C130 | AOH | FA8625-19-F-3805 |  | C005 | ITEM MANAGE | 2020-09-30 |  | Kathleen M Atkins | AT RISK |  |  | -1 |  | Alicia N Walker | ITEM MANAGER | ITEM MANAGER | 1 | 1 | U | 2020-09-30 |  | FA8625-19-F-3805NoneC0052020-09-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 1500 | ALL WORK | 2020-06-24 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | AC 6 MOD Ahead of schedule | -1 |  | Alicia N Walker | OPTION FIVE - MODIFICATION INSTALLATION AIRCRAFT 6 |  | 1 | 2 | U | 2020-06-24 |  | FA8509-19-F-0001None15002020-06-24 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 1600 | ALL WORK | 2020-09-23 |  | Jeff T Vach | AT RISK |  |  | -1 |  | Alicia N Walker | OPTION SIX- MODIFICATION INSTALLATION AIRCRAFT #7 |  | 1 | 2 | U | 2020-09-23 |  | FA8509-19-F-0001None16002020-09-23 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 4500 | SERVICE | 2020-06-24 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | O&A Work associated with MOD of AC 6 | -1 |  | Alicia N Walker | OVER AND ABOVE WORK (O&AW) (SUPPORTING AIRCRAFT #6 MODIFICATION INSTALLATION) |  | 1 | 2 | U | 2020-06-24 |  | FA8509-19-F-0001None45002020-06-24 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8509-19-F-0001 | C130 | AOH | FA8509-19-F-0001 |  | 4600 | SERVICE | 2020-09-23 |  | Jeff T Vach | AT RISK |  |  | -1 |  | Alicia N Walker | OVER AND ABOVE WORK (O&AW) (SUPPORTING AIRCRAFT #7 MODIFICATION INSTALLATION) |  | 1 | 2 | U | 2020-09-23 |  | FA8509-19-F-0001None46002020-09-23 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1401 | ANALYSIS | 2020-08-18 |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track | -3 |  | Mariah Callins | OPTION YEAR 3 ENGINEERING AND LOGISTICS SUPPORT |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000None14012020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1403 | MANUAL | 2020-08-15 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -4 |  | Mariah Callins | OPTION YEAR 3 HC/MC/AC TECHNICAL MANUAL CONTRACT REQUIREMENTS |  | 1 | 1 | U | 2020-08-15 |  | FA8625-16-F-7000None14032020-08-15 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1407 | PROGRAM | 2020-08-18 |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track | -3 |  | Mariah Callins | OPTION YEAR 3 RELIABILITY MAINTAINABILITY PROGRAM |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000None14072020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 1410 | OPTION YEAR | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -3 |  | Mariah Callins | OPTION YEAR 3 FIELD SERVICE REPRESENTATIVE - EGLIN |  | 1 | 1 | U | 2020-08-18 |  | FA8625-16-F-7000None14102020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 3401 | OPTION YEAR |  |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track |  |  | Mariah Callins | OPTION YEAR 3 TRAVEL |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None3401None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4404 | CPFF |  |  | Chris Price | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 3 - DIMINISHING MANUFACTURING SOURCES STUDIES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None4404None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4405 | OPTION YEAR |  |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track |  |  | Mariah Callins | OPTION YEAR 3 - ENGINEERING SUPPORT SERVICES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None4405None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4407 | CPFF |  |  | Chris Price | AT RISK |  |  |  |  | Mariah Callins | OPTION YEAR 2 BU 7/8.1 RETROFIT DMS STUDIES |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None4407None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4501 | DEFICIENCY |  |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track |  |  | Mariah Callins | DEFICIENCY REPORTING (DR) OPTION YEAR 2 (CPFF) |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None4501None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7000 | C130 | AOA | FA8625-16-F-7000 |  | 4502 | DR TRAVEL ( |  |  | Jim Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track |  |  | Mariah Callins | DR TRAVEL (OPTION) |  | 1 | 1 | U | 2020-08-18 | 2020-08-18 | FA8625-16-F-7000None4502None
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1036 | HC/MC-130J | 2020-07-31 | 2019-08-18 | Jackie L Macedonia | AT RISK | Contract Modification Expected to Change PoP Date | Request submitted to PCO on 12 May to extend POP through 31 July to account for PCOL 20-0040 disposition. | -1 | Sonya J Young | Brittany N Scott | HC/MC-130J YEAR 2 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-07-31 |  | FA8625-16-F-7150None10362020-07-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1039 | AC-130J YEA | 2020-06-09 | 2019-08-18 | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Pubs on track, requires CoC at end of PoP | 0 | Sonya J Young | Brittany N Scott | AC-130J YEAR 2 TECHNICAL MANUAL & DATA (FLIGHTPPP) |  | 1 | 1 | J | 2020-06-09 |  | FA8625-16-F-7150None10392020-06-09 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1048 | UPDATE HYPE | 2020-09-30 |  | Jackie L Macedonia | AT RISK |  |  | -1 |  | Brittany N Scott | AC-130J UPDATE HYPERLINK |  | 1 | 1 | J | 2020-09-30 |  | FA8625-16-F-7150None10482020-09-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1055 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -1657 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (NON-IPB) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10552020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1056 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -28 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB < 50 PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10562020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1057 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -49 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB 50+ PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10572020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1058 | HC/MC-130J | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -1934 |  | Brittany N Scott | HC/MC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10582020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1059 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -3035 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (NON-IPB) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10592020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1060 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -28 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB < 50 PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10602020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1061 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -1550 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (IPB 50+ PGS) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10612020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1062 | AC-130J OPT | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | -4030 |  | Brittany N Scott | AC-130J OPTION YEAR 3 TECHNICAL MANUAL & DATA (FLIGHT PPP) |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10622020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-16-F-7150 | C130 | AOA | FA8625-16-F-7150 |  | 1071 | PROPOSAL PR | 2020-08-18 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CoC on track for on time completion | 0 |  | Brittany N Scott | PROPOSAL PREPARATION |  | 1 | 1 | J | 2020-08-18 |  | FA8625-16-F-7150None10712020-08-18 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2001 | FY18 HC-130 | 2020-07-31 |  | James B Armor | ON TIME | DD250 Accepted In WAWF | A/C 5897, Aircraft DD250 Accepted on 5/20/20 | -1 |  | Mariah Callins | FY17 C-130J-30 AIRCRAFT |  | 1 | 1 | J | 2020-07-31 |  | FA8625-17-F-7010None20012020-07-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2003 | AIRCRAFT | 2020-09-30 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5903 | -1 |  | Mariah Callins | FY17 MC-130J AIRCRAFT |  | 1 | 1 | J | 2020-09-30 |  | FA8625-17-F-7010None20032020-09-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-17-F-7163 | C130 | AOA | FA8625-17-F-7163 |  | 0001 | CIP-01 SOFT | 2020-08-31 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | New date due to added RMM cards | -1 |  | Belinda C Young | CIP-01 SOFTWARE MERGER |  | 1 | 1 | J | 2020-08-31 |  | FA8625-17-F-7163None00012020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-17-F-7163 | C130 | AOA | FA8625-17-F-7163 |  | 0002 | OVER AND AB |  |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Over and Above |  |  | Belinda C Young | OVER AND ABOVE |  | 1 | 1 | J | 2020-08-31 | 2020-08-31 | FA8625-17-F-7163None0002None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1623 | UMSC KC-130 |  | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Lot 1 RoR USMC Services as required, CoC to close out |  |  | Mary Kathleen Chaney | ICS ROR - LOT 1 - OPTION YEAR 1 - USMC KC-130J |  | 1 | 1 | L | 2020-07-31 | 2020-07-31 | FA8625-18-F-7001None1623None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1801 | CNI-SP LIFE | 2020-08-30 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - C130J (STRETCH/SHORT) |  | 1 | 1 | L | 2020-08-30 |  | FA8625-18-F-7001None18012020-08-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1803 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - USMC - KC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001None18032020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1804 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - USCG HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001None18042020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1806 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI SP - LIFETIME BUY - AFSOC MC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001None18062020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1807 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - ACC HC-130J |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001None18072020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 1808 | CNI-SP LIFE | 2020-08-31 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track, Combo DD250 planned | -1 |  | Mary Kathleen Chaney | CNI-SP LIFETIME BUY - SYSTEMS INTEGRATION MGMT |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7001None18082020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2101 | UPGRADE | 2020-06-30 | 2020-06-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | COC for CEVA Support Service | -1 |  | Mary Kathleen Chaney | KITS - LOT 1 - CEVA SUPPORT |  | 1 | 1 | L | 2020-06-30 |  | FA8625-18-F-7001None21012020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2111 | BLOCK UPGRA | 2020-06-03 | 2020-06-30 | James H Porter | LATE | Other | Late due to constraints at CEVA. | -2 |  | Mary Kathleen Chaney | KITS - C130J - (STRETCH) - GROUP A - QTY 16 |  | 1 | 1 | L | 2020-06-03 |  | FA8625-18-F-7001None21112020-06-03 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2112 | BLOCK UPGRA | 2020-06-03 | 2020-06-30 | James H Porter | LATE | Other | Late due to constraints at CEVA. | -2 | Daniel L Kiefer | Mary Kathleen Chaney | KITS - C130J - (STRETCH) - GROUP B - QTY 16 |  | 1 | 1 | L | 2020-06-03 |  | FA8625-18-F-7001None21122020-06-03 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2512 | UCA - TRAIN | 2020-07-02 | 2020-07-02 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Still on UCA, will require Defin to DD250 | -1 |  | Mary Kathleen Chaney | UCA - TRAINER DEVICE HARDWARE FROM LOT 1 - AMC C-130J (STRETCH/SHORT) |  | 1 | 1 | L | 2020-07-02 |  | FA8625-18-F-7001None25122020-07-02 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2812 | UPGRADE | 2020-06-30 | 2020-05-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Upgrade Services CLIN, will close if not used at end of PoP | -2 |  | Mary Kathleen Chaney | GFE HUD HEU UPGRADE - C130J - SHORT |  | 1 | 1 | L | 2020-06-30 |  | FA8625-18-F-7001None28122020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4006 | OVER & ABOV |  |  | Jim Porter | AT RISK |  |  |  | Tim Farmer | Mariah Callins | OVER AND ABOVE (O&A) - INSTALLS |  | 1 | 1 | U | 2020-06-30 | 2020-06-30 | FA8625-18-F-7019None4006None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4007 | ADS-B OUT I |  |  | Jim Porter | [5 empty] | Mariah Callins | ADS-B OUT INSTALL LABOR - OPTION |  | 1 | 1 | U | 2020-06-30 | 2020-06-30 | FA8625-18-F-7019None4007None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4008 | ADS-B OUT I |  |  | Jim Porter | [5 empty] | Mariah Callins | ADS-B OUT INSTALLS TRAVEL DEPLOYMENT - OPTION |  | 1 | 1 | U | 2020-06-30 | 2020-06-30 | FA8625-18-F-7019None4008None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4009 | ADS-B OUT I |  |  | Jim Porter | [5 empty] | Mariah Callins | ADS-B OUT INSTALLS TRAVEL INCIDENTALS - OPTION |  | 1 | 1 | U | 2020-06-30 | 2020-06-30 | FA8625-18-F-7019None4009None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | 4102 | INTERIM CON |  |  | Jim Porter | AT RISK |  |  |  | Tim Farmer | Mariah Callins | INTERIM CONTRACTOR SUPPORT (ICS) - OPTION YEAR 1 |  | 1 | 1 | U | 2020-09-30 | 2020-09-30 | FA8625-18-F-7019None4102None
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7028 | C130 | AOA | FA8625-18-F-7028 |  | 1002 | SERV | 2020-09-30 |  | Jim Armor | AT RISK |  |  | -8 |  | Mary Kathleen Chaney | FY19 C-130J-30 (AMC/ANG) DELIVERY PERFORMANCE INCENTIVE |  | 1 | 1 | L | 2020-09-30 |  | FA8625-18-F-7028None10022020-09-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1003 | MC-130J SEV | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to complete on time. | 0 | Mark P Lewandowski | Brittany N Scott | MC-130J SEVEN INC 1-2 AND LAIRCM GROUP A INSTALLS |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7162None10032020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1004 | MC-130J SEV | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to complete on time. | 0 | Mark P Lewandowski | Brittany N Scott | MC-130J SEVEN LAIRCM GROUP B INSTALLS |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7162None10042020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 1005 | ADS-B OUT I | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to complete on time. | 0 | Mark P Lewandowski | Brittany N Scott | ADS-B OUT INC 1-2 (INSTALL ADS-B OUT DURING INC 1-2 CONFIGURATION) |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7162None10052020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4001 | MC-130J INC | 2020-07-31 |  | Jackie L Macedonia | AT RISK | Contract Modification Expected to Change PoP Date | Final Inc 1-2 Aircraft expected to deliver in June. O&A likely to be extended to cover Longeron repairs. Discussions ongoing with USG. | -1 | Mark P Lewandowski | Brittany N Scott | MC-130J INC1-2 OVER AND ABOVE CARE & MAINTENANCE |  | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7162None40012020-07-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4002 | MC-130J SIX | 2020-06-30 |  | Jackie L Macedonia | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Final aircraft tracking to complete on time. | 0 | Mark P Lewandowski | Brittany N Scott | MC-130J SIX INC 1-2 LSPR/CIUR INSTALLS |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7162None40022020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 5001 | ADS-B OUT/O | 2020-06-30 |  | Jackie L Macedonia | AT RISK | Contract Modification Expected to Change PoP Date | 5863 tracking to complete in October. POP extension required. | -1 |  | Brittany N Scott | ADS-B OUT/OPTION X INSTALL ON 16-5863 |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7162None50012020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | 1005 | CEVA AND LL | 2020-06-30 | 2022-06-30 | Brian D Ginn | AT RISK | Contract Modification Expected to Change PoP Date | PoP extension requested | -1 |  | Jordan R Smythe | RAAF LONG LEAD ITEMS CEVA AND ITEM MANAGEMENT |  | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401None10052020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A001 | BLANKING UN | 2020-06-20 | 2020-06-05 | Brian D Ginn | ON TIME | DD250 Accepted In WAWF | Shipped 6/1/2020; DO 83064267; PN 357048-001 / SO 10069076 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 357048-001 | 1 | 1 | J | 2020-06-20 |  | FA8625-18-F-7401NoneA0012020-06-20 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A002 | PILOT ABY | 2020-06-20 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Pending for DCMA Visual Inspection, DO 83024043 & 83026592; PN 698261-1 / SO 10069075 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 698261-1 | 1 | 1 | J | 2020-06-20 |  | FA8625-18-F-7401NoneA0022020-06-20 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | A003 | COPILOT | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Obtaining CoCs, DO 83024186; PN 698261-2 / SO 10069074 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT A - BLOCK 7.0 SPARES | 698261-2 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneA0032020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C001 | SPEAKER | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Pending for DCMA Visual Inspection, DO 83025870; PN 12890 / SO 10069073 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 12890 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0012020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C002 | CARGO AREA | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Pending for DCMA Visual Inspection, DO 83055984; PN 12891 / SO 10069072 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 12891 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0022020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C003 | PRINTER | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Obtaining CoC for Acceptance, DO 83025880 PN 42820325 SO 10069071 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 42820325 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0032020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C004 | FAN | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Obtaining CoC for DCMA Acceptance, DO 83025898 PN 645055-3 SO 10069070 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 645055-3 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0042020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C005 | PANEL ABY | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Obtaining CoC for DCMA Acceptance, 5/14/20. DO 83023684 PN 697906-21 SO 10069069 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697906-21 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0052020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C006 | PANEL ABY | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Pending for DCMA Visual Inspection, DO 83023691; PN 697906-23 / SO 10069068 | -1 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697906.23 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0062020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C007 | HUD ELECTRO | 2020-06-30 |  | Brian D Ginn | AT RISK |  |  | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 697940.21 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0072020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C008 | DIGITAL SWI | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Pending for DCMA Visual Inspection, DO 83023740; PN 698286-103 / SO 10069066 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 698286-103 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0082020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C009 | DIGTAL CREW | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | DCMA accepted 2 each. 1 more pending for DCMA Visual Inspection, 83026248; PN 698286-203 / SO 10069065 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 698286-203 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC0092020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C00A | VHF DATA RA | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; Obtaining CoC for WAWF submittal. DO 83025915; PN 965-1696-081 / SO 10069064 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | 965-1696-081 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC00A2020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | C00B | FLOODLIGHT | 2020-06-30 | 2020-06-11 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; QA reviewing for WAWF submittal. DO 83025919; PN S2491-101 / SO 10069063 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS EXHIBIT C - BLOCK 8.1 SPARES | S2491-101 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneC00B2020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7401 | C130 | AOA | FA8625-18-F-7401 |  | D001 | PROCESSOR | 2020-06-30 | 2020-06-17 | Brian D Ginn | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track: Pending for DCMA Visual Inspection P/N 698266-1 / 1 ea DO 83096703 & 1 ea DO 83100207, SO 10069102 | 0 |  | Jordan R Smythe | RAAF LONG LEAD TIME ITEMS: EXHIBIT D - SPECIAL MISSION DISPLAY PROCESSOR | 698266-1 | 1 | 1 | J | 2020-06-30 |  | FA8625-18-F-7401NoneD0012020-06-30 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | 1001 | CEVA & ITEM | 2020-07-31 |  | Cindy Failor | AT RISK | Other | CLIN for CEVA/IA tied to open deliverable CLINs. Cannot DD250 until all other CLINs are delivered. | -1 |  | Olivia M Haller | FMS ISAREL SPARES CEVA AND ITEM MANAGEMENT |  | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801None10012020-07-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0001 | INITIAL INS |  |  | Jim Porter | AT RISK |  |  |  |  | Mary Kate Chaney | INITIAL INSTALLATION OF 7/8.1 BLOCK UPGRADE KITS |  | 1 | 1 | J | 2020-09-01 | 2020-09-01 | FA8625-19-F-7033None0001None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0004 | PHYSICAL CO |  |  | Jim Porter | AT RISK |  |  |  |  | Mary Kate Chaney | PHYSICAL CONFIGURATION AUDIT |  | 1 | 1 | J | 2020-08-10 | 2020-08-10 | FA8625-19-F-7033None0004None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0005 | INVENTORY C |  | 2020-05-29 | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | ICP Support Services, CoC to close out last day of PoP |  |  | Mary Kate Chaney | INVENTORY CONTROL POINT (ICP) SUPPORT | INVENTORY CONTROL POINT ( | 1 | 1 | J | 2020-07-31 | 2020-07-31 | FA8625-19-F-7033None0005None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7802 | C130 | AOA | FA8625-19-F-7802 |  | 1000 | MULTI FUNCT |  |  | Cindy Failor | AT RISK | DD250 Accepted In WAWF |  |  |  | Olivia M Haller | FMS ISRAEL MULTI FUNCTIONAL SERVICE ENGINEER YEAR 1 |  | 1 | 1 | J | 2020-09-30 | 2020-09-30 | FA8625-19-F-7802None1000None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4010 | CONTRACTOR | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK | Contract Mod Requested | Contract mod requested for PoP extension to 31 December 2020 | -3 |  | Reda R Belmaachi | CONTRACTOR MAINTENANCE TEAM |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905None40102020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4020 | LOGISTICS S | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK | Contract Mod Requested | Contract mod requested for PoP extension to 31 December 2020 | -3 |  | Reda R Belmaachi | LOGISTICS SUPPORT REPRESENTATIVE |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905None40202020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4030 | REPAIR OF R |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | REPAIR OF REPAIRABLES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-7905None4030None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4040 | INTEGRATED | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK | Contract Mod Requested | Contract mod requested for PoP extension to 31 December 2020 | -3 |  | Reda R Belmaachi | INTEGRATED LOGISTICS SUPPORT |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905None40402020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4050 | CONSUMABLE |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | CONSUMABLE REPLENISHMENT SPARES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-7905None4050None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4060 | ENGINEERING | 2020-08-31 |  | Chris G Vachtsevanos | AT RISK | Contract Mod Requested | Contract mod requested for PoP extension to 31 December 2020 | -3 |  | Reda R Belmaachi | ENGINEERING TECHNICAL SUPPORT |  | 1 | 1 | U | 2020-08-31 |  | FA8625-19-F-7905None40602020-08-31 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4070 | PUBLICATION |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | PUBLICATION UPDATES |  | 1 | 1 | U | 2020-08-31 | 2020-08-31 | FA8625-19-F-7905None4070None
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4080AA | NOUN |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | VALUE ADDED TAX - CONTRACTOR MAINTENANCE TEAM |  | 1 | 1 | U | 2020-08-30 | 2020-08-30 | FA8625-19-F-7905None4080AANone
ALX | AMMM | FA8625-16-D-6458 | FA8625-19-F-7905 | C130 | AOA | FA8625-19-F-7905 |  | 4080AB | NOUN |  |  | Chris G Vachtsevanos | AT RISK |  |  |  |  | Reda R Belmaachi | VALUE ADDED TAX - LOGISTICS SUPPORT REPRESENTATIVE |  | 1 | 1 | U | 2020-08-30 | 2020-08-30 | FA8625-19-F-7905None4080ABNone
ALX | AMMM | FA8625-16-D-6458 | FA8625-20-F-8001 | C130 | AOH | FA8625-20-F-8001 |  | 5002 | PROPOSAL PR | 2020-06-19 |  | Kathleen M Atkins | AT RISK | DD250 Submitted, Awaiting DCMA approval | DD250 Submitted in WAWF on 5/22/2020. Awaiting DCMA Acceptance. | 0 |  | Alicia N Walker | PROPOSAL PREPARATION |  | 1 | 1 | J | 2020-06-19 |  | FA8625-20-F-8001None50022020-06-19 00:00:00
ALX | AMMM | FA8625-16-D-6458 | FA8629-19-F-7167 | C130 | AOA | FA8629-19-F-7167 |  | 0003AB | NOUN | 2020-09-01 |  | Jim Armor | AT RISK |  |  | -1 |  | Brittany N Scott | TRIAL KIT INSTALL FOR MC-130J TO AC-130J CONVERSION DELTA KIT |  | 1 | 1 | J | 2020-09-01 |  | FA8629-19-F-7167None0003AB2020-09-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2002 | AIRCRAFT | 2020-08-31 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5898 | -1 |  | Mariah Callins |  |  | 1 | 1 | J | 2020-08-31 |  | FA8625-17-F-7010None20022020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-17-F-7010 | C130 | AOA | FA8625-17-F-7010 |  | 2002 | AIRCRAFT | 2020-09-30 |  | Jeff T Vach | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5901 | -1 |  | Mariah Callins |  |  | 1 | 1 | J | 2020-09-30 |  | FA8625-17-F-7010None20022020-09-30 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2141 | BLOCK UPGRA | 2020-06-03 |  | James H Porter |  |  |  | -1 |  | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-06-03 |  | FA8625-18-F-7001None21412020-06-03 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | 2401 | SPARES | 2020-09-01 |  | James L Porter |  |  |  | -1 |  | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-09-01 |  | FA8625-18-F-7001None24012020-09-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H001 | GPS/WAAS | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H002 | EMU | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0022020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H003 | PMD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H004 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H005 | CS AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H006 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Douglas A Davidi | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H007 | RECEPATCLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H008 | HAND MICROP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H010 | MEMORY CD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H011 | DIPLEXER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H012 | UNIT MOUNT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-00 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0122020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H013 | TETHER CABL | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H014 | COMBINER RF | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H015 | HIGH PWR RE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0152020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H016 | TRAY ASSY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0162020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H017 | TRAY ASSY | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0172020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H018 | BLANKET UN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0182020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0192020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H020 | MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0202020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H021 | DATA UNIT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0212020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0222020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H023 | SPLITTER | 2020-07-31 | 2020-07-01 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | Meeting with USG 3/20/2019 to work out new POP extension date | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0232020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H024 | MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0242020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H025 | BROADBAND | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0252020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H026 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0262020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H027 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; DO 82545345 processing through shipping | -3 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0272020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H028 | COVER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0282020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H029 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0292020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H030 | CIRCUIT BK | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DOs 82976563, 82976824, 83001307 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0302020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H032 | PILOT CONTR | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0322020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H033 | CONTROL ABY | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0332020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H034 | SPLINE | 2020-07-31 |  | James H Porter | AT RISK |  | Meeting with USG 3/20/2019 to work out new POP extension date | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0342020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H035 | CNI-SP-COUN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0352020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H037 | SNDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0372020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H038 | VIDEO SWITC | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0640 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0382020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H039 | TRAY ASSY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0392020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H040 | DIGITAL SWI | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0402020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H041 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0412020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H042 | VHF DATA RA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0422020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H043 | PLUGA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0432020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H044 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0442020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H045 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0452020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0462020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0472020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H048 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0482020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H049 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0492020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H050 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0502020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H051 | SCREW | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0512020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H052 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0522020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H053 | SPACER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0532020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H054 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0542020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJF4V71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0552020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H056 | FLOODLIGHT | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0562020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H057 | L-BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0572020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0582020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H059 | SPEAKER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0592020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H060 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneH0602020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H203 | PMD | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H205 | CS AMP | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD 4/28/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H210 | PCMCIA MEMO | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H211 | DIGITAL SWI | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H213 | PMD TETHER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H214 | COMBINER RF | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H216 | MOUNTING TR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 4/30/20 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039974 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H218 | PRG INT BLA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H221 | SATELLITE D | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H222 | COUPLER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H223 | SLITTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0786 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H224 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0788 | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0612 | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H226 | PRINTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0642 | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H227 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -3 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H228 | HPA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83012870 | -1 |  | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H229 | PMD DUST CO | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2292020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H230 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H231 | CIRCUIT BRE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2312020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H233 | PILOT CONTR | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to Sept 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2332020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H234 | COPILOT CON | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2342020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H236 | CNI-SP COUN | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0622 | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2362020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H239 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H241 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0613 | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2412020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H242 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -2 |  | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2422020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H243 | DIGIAL CREW | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts... mod received moved to September 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2432020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2442020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2452020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H246 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2462020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H247 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0782 | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2472020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H248 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2482020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H249 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2492020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H250 | PLUG | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0620 | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2502020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H251 | PLUG CONNEC | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2512020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H252 | PLUG CONNEC | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2522020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H253 | SCREW | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0619 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2532020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H254 | TRAY ASSEMB | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD : 6/2020.. mod received moved to September 2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2542020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H255 | SPACER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0618 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2552020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H256 | TRAY ASSEMB | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2562020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0617 | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2572020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H258 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2582020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H259 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2592020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H260 | GPS/WAAS AN | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/2020 | -2 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2602020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H261 | SPEAKER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2612020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | H262 | ANTENNA | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83061804 | -1 |  | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneH2622020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J002 | EMU | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0022020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J003 | PMD | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J004 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11508080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J005 | CS AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J006 | PA PRE-AMP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J007 | RECEPTACLE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J008 | HAND MICROP | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J010 | PCMCIA MEMO | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J011 | DIPLEXER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J012 | PMD UNIT MO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0122020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J013 | PMD TETHER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J014 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J015 | HIGH PWR RE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0152020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J016 | MOUNTING TR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0162020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J017 | MOUNTING TR | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0172020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J018 | BLANKET UN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0182020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0192020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J020 | COM MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0202020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J021 | SATELLITE D | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0212020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0222020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J023 | SPLITTER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0232020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J024 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0242020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J025 | SWITFT BROA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0252020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J026 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0262020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J027 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0272020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J028 | PMD DUST CO | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0282020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J029 | PLUG C | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0292020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J030 | CIR BREAKER | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track Processing through shipping DO 82967973 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0302020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J032 | PILOT CON | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0322020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J033 | PILOT CON | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0332020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J034 | SPLINE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0342020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J035 | CNI-SP COUN | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0352020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J037 | SMDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0372020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J039 | TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0392020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J040 | DIGITAL SWI | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82966081 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0402020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J041 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0412020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J042 | VHF DATA RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0422020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J043 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0432020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J044 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0442020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J045 | PLUG | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0452020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0462020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0472020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J048 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0482020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J049 | PLUG CONN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0492020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J050 | PLUG CONN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0502020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J051 | SCREW | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0512020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J052 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0522020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J053 | SPACER | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 11/19/2018 / CVA0019 | -2 |  | Mary Kathleen Chaney |  | NAD43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0532020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J054 | TRAY ASBY | 2020-07-31 | 2020-07-31 | James H Porter | LATE |  | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0542020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJF6V71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0552020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J056 | FLOODLIGHT | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0562020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J057 | L BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0572020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0582020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J059 | SPEAKER | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0592020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | J060 | ANTENNA | 2020-07-31 | 2020-07-31 | James H Porter | AT RISK | Contract Modification Expected to Change PoP Date | MOD signed as of 5/20/2019 (Provided a copy to Tavia) New POP 07/31/2020 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718.1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneJ0602020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K002 | EMU | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0022020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K003 | PMD | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K004 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K005 | CS AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K006 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K007 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K008 | HAND MICROP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K009 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K010 | PCMCIA MEMO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K011 | DIPLEXER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 222643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K012 | PMD UNIT MO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0122020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K013 | PMD TETHER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K014 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K015 | HIGH PWR RE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0152020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K016 | MOUNT TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0162020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K017 | MOUNT TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0172020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K018 | BLANKET UN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0182020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K019 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0192020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K020 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0202020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K021 | SATELLITE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0212020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K022 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0222020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K023 | SPLITTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0232020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K024 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0242020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K025 | SWIFT BROA | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82568202 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0252020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K027 | HIGH GAIN A | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 51338-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0272020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K029 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0292020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K032 | PILOT CONTR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0322020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K033 | COPILOT CON | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0332020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K034 | SPLINE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0342020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K035 | CNI-SP COUN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0352020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K037 | SMDP TRAY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0372020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K038 | VIDEO SWITC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0382020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K039 | TRAY ASSY/V | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0392020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K040 | DIGITAL SWI | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0402020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K041 | DIGITAL CRE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0412020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K042 | VHF DATA RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0422020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K043 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0432020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K044 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0442020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K045 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0452020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K046 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0462020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K047 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0472020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K048 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0482020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K049 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0492020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K050 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0502020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K051 | SCREW | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0512020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K052 | TRAY ASSEMB | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0522020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K053 | SPACER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0532020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K054 | TRAY ASSEMB | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0542020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K055 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0552020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K056 | FLOODLIGHT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0562020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K057 | L-BAND ANTE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0572020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K058 | GPS/WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0582020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K059 | SPEAKER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0592020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K060 | ANTENNA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneK0602020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K201 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83050376 | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K207 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K210 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K213 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K216 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K221 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K227 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K228 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2292020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K232 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2322020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K233 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2332020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2342020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2372020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K240 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Working with buyer to bring in parts.. mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2402020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K241 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts..mod received moved to September 2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2412020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K242 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2422020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K243 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2432020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2442020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2452020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K246 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2462020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K247 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2472020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K248 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2482020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K249 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2492020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K250 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2502020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K251 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0625 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2512020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K252 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2522020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K253 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0676 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2532020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K254 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0675 | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2542020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K255 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2552020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K256 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2562020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0560 | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2572020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K258 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2582020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K259 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2592020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | K260 | ANTENNA | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneK2602020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L001 | GPS/WAAS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L002 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 11S08080090C34 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0022020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L003 | CS AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L004 | PA PRE-AMP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L005 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L006 | HAND MICROP | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L007 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 200-8686-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L008 | PCMCIA MEMO | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 207025-10101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L009 | DIPLEXER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L010 | COMBINER RF | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L011 | HIGH PWR RE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L012 | BLANKET UNI | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0122020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L013 | AMPLIFIER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L014 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L015 | SATELLITE D | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0152020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L016 | COUPLER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0162020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L017 | SPLITTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0172020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L018 | CON MODULE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0182020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L020 | PRINTER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0202020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L021 | ANTENNA ASS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0212020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L022 | PLUGS | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0222020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L023 | CIR BREAKER | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82967974 | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0232020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L024 | PUBLIC AD A | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 697966-301 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0242020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L025 | PILOT CONTR | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0252020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L026 | COPILOT CON | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0262020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L027 | SPLINE | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 3/14/2019 / CVA0197 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0272020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L028 | CNI-SP COUN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0282020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L029 | DIITAL SWIT | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83027027 | -1 |  | Mary Kathleen Chaney |  | 698286-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0292020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L030 | DIGITAL CRE | 2020-07-31 | 2020-07-31 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031417 | 0 |  | Mary Kathleen Chaney |  | 698286-201 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0302020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L031 | VHF DTAT RA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0312020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L032 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | BKAD1-125-3030RF0 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0322020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L033 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0332020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L034 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0342020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L035 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0352020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L036 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0362020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L037 | PLUG | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0372020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L038 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0382020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L039 | PLUG CONNEC | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0392020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L040 | SCREW | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0402020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L041 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0412020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L042 | SPACER | 2020-07-31 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 3/14/2019 / CVA0184 | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0422020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L043 | TRAY ASBY | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0432020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L044 | RECEPTACLE | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0442020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L045 | FLOODLIGHT | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0452020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L046 | GPS.WAAS AN | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0462020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L047 | SPEAKER | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0472020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L048 | ANTENNA | 2020-07-31 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | VFH10-718-1 | 1 | 1 | L | 2020-07-31 |  | FA8625-18-F-7001NoneL0482020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/14/2020 / CVA0544 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L213 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/9/2020 / CVA0671 | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83051349 | 0 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83051348 | 0 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L217 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Working with buyer to bring in parts; ECD: 6/30/2020 | -2 |  | Mary Kathleen Chaney |  | 698286-105 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | L220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneL2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0630 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M204 | PAPRE-AMP | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0632 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M205 | HAND MICROP | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M206 | DIGITAL SWI | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955972 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0634 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M208 | COMPACT FLA | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604373-016 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M209 | COMBINER RF | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M210 | TX COUPLER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020/ CVA0705 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M211 | PANEL ASSEM | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3351980-53 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M212 | CONTROL PAN | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 3365866-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82955983 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M214 | HIGH POWER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/11/2020 / CVA0699 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M215 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0707 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M216 | SATELLITE D | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0702 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M217 | COUPLER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82955988 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M218 | SPLITTER | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0698 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M219 | CONFIGRATIO | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/22/2020 / CVA0701 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0700 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M221 | ETHERNET | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M222 | PRINTER | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M223 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DOs 82974394, 83022241 and 83021963 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M224 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M225 | PMD DUST CO | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82918419 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M226 | PANEL ASSEM | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD: 5/15/2020 | -7 | Tim Farmer | Mary Kathleen Chaney |  | 697906-21 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M227 | PANEL ASSEM | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -7 | Tim Farmer | Mary Kathleen Chaney |  | 697906-23 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M228 | HUD ELECT U | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83129880 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 697940-19 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M230 | PILOT CONTR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M231 | COPILOT CON | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 6/2020 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2312020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M235 | DIGITAL SW | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83129889 | -6 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M236 | DIGITAL CRE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD: 5/15/2020 | -13 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2362020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M237 | VHF DATA RA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0636 CVA0637 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2372020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M238 | FLOODLIGHT | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2382020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M239 | L-BAND ANTE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2402020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M241 | SPEAKER | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2412020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | M242 | ANTENNA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0713 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneM2422020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82956015 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604373-016 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 5/8/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0714 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/9/2020 / CVA0716 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0709 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0710 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N213 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; ECD 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 5/8/2020 | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N221 | DIGITAL CRE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD 6/2020 | -5 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0565 | 0 | Tim Farmer | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | N226 | ANTENNA | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/22/2020 / CVA0706 | 0 | Tim Farmer | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneN2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -1 |  | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P203 | HIGH POWER | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82957945 | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82957943 | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0711 | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0787 | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD: 5/15/2020 | -3 |  | Mary Kathleen Chaney |  | 697906-21 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts ECD : 6/2020 | -3 |  | Mary Kathleen Chaney |  | 697906-23 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -3 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -3 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | P219 | GPS/WAAS AN | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneP2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R202 | PIN, CONTRA | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R203 | EMU | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82976599 | -1 |  | Mary Kathleen Chaney |  | 3361873-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82976575 | -1 |  | Mary Kathleen Chaney |  | 3365774-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82976588 | -1 |  | Mary Kathleen Chaney |  | 3365776-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R212 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3366233-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R214 | BACKSHELL | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R215 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R216 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 650HS010NF09 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | 0 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R219 | ADAPTER HUB | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0502 | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0503 | 0 |  | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R227 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R228 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2292020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R231 | PLUG | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2312020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LS35301B06AY | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2322020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R233 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | M83536-16-022M | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2332020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MS21042-04 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2342020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R235 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82901608 | 0 |  | Mary Kathleen Chaney |  | MS21042-06 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | MS35206-245 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2362020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS1149DN832H | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2372020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS600-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2382020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | R239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | NAS601-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneR2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S202 | PIN, CONTRA | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0562 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0564 | 0 | Tim Farmer | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3361873-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S208 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S210 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365774-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365776-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3365972-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S214 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 3366233-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82852839 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S217 | ETHERNET | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 650HS010NF09 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S219 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring parts in | -1 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S221 | ADAPTER HUB | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82852851 | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S222 | CNI-SP COUN | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S227 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S228 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S229 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2292020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S231 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2312020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S232 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2322020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S233 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2332020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S234 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | LS35301B06AY | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2342020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | M83536-16-022M | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0563 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS21042-04 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2362020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S237 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0558 | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS21042-06 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2372020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S238 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | MS35206-245 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2382020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS1149DN832H | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S240 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS600-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2402020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | S241 | SCREW | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | NAS601-4P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneS2412020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0760 | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T203 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0767 | 0 |  | Mary Kathleen Chaney |  | 100-604003-054 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T204 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0665 | 0 |  | Mary Kathleen Chaney |  | 111S08080090C34 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12890 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T206 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T207 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0666 | 0 |  | Mary Kathleen Chaney |  | 1499598 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0667 | 0 |  | Mary Kathleen Chaney |  | 18226G15 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973325 | 0 |  | Mary Kathleen Chaney |  | 200-86686-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82978401 | -1 |  | Mary Kathleen Chaney |  | 207025-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T211 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973294 | 0 |  | Mary Kathleen Chaney |  | 2292643-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973298 | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973300 | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 82973302 | 0 |  | Mary Kathleen Chaney |  | 300114-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T215 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts.. mod received moved to September 2020 | -1 |  | Mary Kathleen Chaney |  | 301706-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T216 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039952 | -1 |  | Mary Kathleen Chaney |  | 3362445-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2162020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T217 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83039955 | 0 |  | Mary Kathleen Chaney |  | 3362445-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2172020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T218 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0608 | 0 |  | Mary Kathleen Chaney |  | 357048-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T219 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0763 | 0 |  | Mary Kathleen Chaney |  | 405014A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2192020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T220 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T221 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405035A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T222 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A002 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405038A003 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T224 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A835 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T225 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 405040A-THD | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T226 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0654 | 0 |  | Mary Kathleen Chaney |  | 42820325 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T227 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82934132 and 83021951 | 1 |  | Mary Kathleen Chaney |  | 513738-519 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T228 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; mod received moved to September 2020 | -1 |  | Mary Kathleen Chaney |  | 513739-512-99 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2282020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T229 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82973257 | 0 |  | Mary Kathleen Chaney |  | 550-601595-000 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2292020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T230 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0663 | 0 |  | Mary Kathleen Chaney |  | 616697173 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2302020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T231 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/17/2020 / CVA0776 | 0 |  | Mary Kathleen Chaney |  | 697941-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2312020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T233 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; mod received moved to September 2020 | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2332020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T234 | SUPPLIES/SE | 2020-07-24 | 2020-09-30 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts; mod received moved to September 2020 | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2342020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T235 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2352020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T236 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0756 | 0 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2362020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T239 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0662 | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2392020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T241 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0650 | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2412020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T242 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted by DCMA on 4/3/2020 / CVA0757 | 0 |  | Mary Kathleen Chaney |  | 698286-107 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2422020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T243 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0758 | 0 |  | Mary Kathleen Chaney |  | 698286-207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2432020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T244 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0759 | 0 |  | Mary Kathleen Chaney |  | 965-1696-081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2442020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T245 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0651 | 0 |  | Mary Kathleen Chaney |  | BKAD1-125-30304F0 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2452020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T246 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | AT RISK |  |  | 0 | Tim Farmer | Mary Kathleen Chaney |  | DPX2NA-67322-463 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2462020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T247 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | DPX2NA-67322-500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2472020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T248 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0657 | 0 |  | Mary Kathleen Chaney |  | LN81003-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2482020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T249 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81003-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2492020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T250 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0660 | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2502020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T251 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | LN81030-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2512020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T252 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0658 | 0 |  | Mary Kathleen Chaney |  | LN81030-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2522020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T253 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0664 | 0 |  | Mary Kathleen Chaney |  | MS51959-44B | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2532020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T254 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0689 | 0 |  | Mary Kathleen Chaney |  | MT6-3310-104 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2542020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T255 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0646 | 0 |  | Mary Kathleen Chaney |  | NAS43DD16-24N | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2552020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T256 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/1/2020 / CVA0648 | 0 |  | Mary Kathleen Chaney |  | P0299-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2562020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T257 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/10/2020 / CVA0691 | 0 |  | Mary Kathleen Chaney |  | RJFTV71G | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2572020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T258 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S2491-101 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2582020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T259 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/3/2020 / CVA0652 | 0 |  | Mary Kathleen Chaney |  | S65-5366-116L | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2592020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T260 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | S67-1575-135 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2602020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T261 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2612020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | T262 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/28/2020 / CVA0768 | 0 |  | Mary Kathleen Chaney |  | VHF10-718-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneT2622020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U201 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031860 | 0 |  | Mary Kathleen Chaney |  | 019512-2081 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U202 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031861 | 0 |  | Mary Kathleen Chaney |  | 019912-2012 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U203 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; processing through shipping DO 83031862 | 0 |  | Mary Kathleen Chaney |  | 100-601978-401 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2032020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO U204 | 0 |  | Mary Kathleen Chaney |  | 245-604319-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U205 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/28/2020 / CVA0796 | 0 |  | Mary Kathleen Chaney |  | 245-604320-001 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U206 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362387-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2062020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 82959705 | 0 |  | Mary Kathleen Chaney |  | 3365561-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 3366110-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U209 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3366233-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U210 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031909 | -2 |  | Mary Kathleen Chaney |  | 360MA060NF1207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2102020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U211 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/23/2020 / CVA0708 | 0 |  | Mary Kathleen Chaney |  | 42740500 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2112020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U212 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2122020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U213 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2132020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U214 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031961 | 0 |  | Mary Kathleen Chaney |  | 698261-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2142020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U215 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts. ECD : 5/15/2020 | -2 |  | Mary Kathleen Chaney |  | 698265-3 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2152020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U218 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031978 | 0 |  | Mary Kathleen Chaney |  | 698266-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2182020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U220 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031981 | 0 |  | Mary Kathleen Chaney |  | 698267-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2202020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U221 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031983 | 0 |  | Mary Kathleen Chaney |  | AC-6Q08SC01-02A | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2212020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U222 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031987 | 0 |  | Mary Kathleen Chaney |  | KIT713030-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2222020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U223 | SUPPLIES/SE | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | KIT713030-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2232020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U224 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031988 | 0 |  | Mary Kathleen Chaney |  | KIT713140-6 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2242020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U225 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031994 | 0 |  | Mary Kathleen Chaney |  | KIT713140-7 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2252020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U226 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83031995 | 0 |  | Mary Kathleen Chaney |  | LN81029-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2262020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | U227 | KIT | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 3362209-5 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneU2272020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V201 | GPS/WAAS | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V202 | PA PRE-AMP | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V204 | PILOT CONTR | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V205 | COPILOT CON | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-103 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V208 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -2 | Tim Farmer | Mary Kathleen Chaney |  | 698286-203 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | V209 | SPEAKER | 2020-07-24 |  | James H Porter |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneV2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X201 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0672 | 0 |  | Mary Kathleen Chaney |  | 100-601967-113 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2012020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X202 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0674 | 0 |  | Mary Kathleen Chaney |  | 12891 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2022020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X204 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-1 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2042020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X205 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; working with buyer to bring in parts | -1 |  | Mary Kathleen Chaney |  | 698261-2 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2052020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X207 | SUPPLIES/SE | 2020-07-24 | 2020-07-24 | James H Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On Track; Processing through shipping DO 83129882 | -1 |  | Mary Kathleen Chaney |  | 698286-107 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2072020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X208 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0678 | 0 |  | Mary Kathleen Chaney |  | 698286-207 | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2082020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7001 | C130 | AOC | FA8625-18-F-7001 |  | X209 | SUPPLIES/SE | 2020-07-24 |  | James H Porter | ON TIME | DD250 Accepted In WAWF | Accepted in WAWF on 4/20/2020 / CVA0673 | 0 |  | Mary Kathleen Chaney |  | SA315P | 1 | 1 | L | 2020-07-24 |  | FA8625-18-F-7001NoneX2092020-07-24 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7012 | C130 | AOA | FA8625-18-F-7012 |  | 2001 | AIRCRAFT | 2020-08-31 |  | James B Armor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | A/C 5900 | -1 |  | Mariah Callins |  |  | 1 | 1 | L | 2020-08-31 |  | FA8625-18-F-7012None20012020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1002AA | SEE CLIN | 2020-07-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-07-01 |  | FA8625-18-F-7014None1002AA2020-07-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-09-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-09-01 |  | FA8625-18-F-7014None1003AA2020-09-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-07-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-07-01 |  | FA8625-18-F-7014None1003AA2020-07-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-06-01 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-06-01 |  | FA8625-18-F-7014None1003AA2020-06-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7014 | C130 | AOA | FA8625-18-F-7014 |  | 1003AA | SEE CLIN | 2020-08-03 |  | James B Armor |  |  |  | 0 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-03 |  | FA8625-18-F-7014None1003AA2020-08-03 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | B015 | SPARE CIVIL | 2020-06-30 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | DO's 83001433 & 83001434 have been submitted to LM QA to be presented to DCMA for acceptance | 0 | Daniel L Kiefer | Mariah Callins |  | 100-601967-113 | 1 | 1 | U | 2020-06-30 |  | FA8625-18-F-7019NoneB0152020-06-30 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | C001 | 100-601967- | 2020-08-31 |  | Jim Porter | AT RISK |  |  | 0 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneC0012020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | C003 | S67-1575-13 | 2020-08-31 |  | Jim Porter | AT RISK |  |  | 0 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneC0032020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D001 | ADS-B OUT N | 2020-08-31 |  | Jim Porter | AT RISK |  |  | -1 | Tim Farmer | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneD0012020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D002 | HC/MC-130J | 2020-08-31 |  | Jim Porter |  |  |  | 0 |  | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneD0022020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D003 | C-130J ADS- | 2020-08-31 |  | Jim Porter |  |  |  | 0 |  | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneD0032020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7019 | C130 | AOA | FA8625-18-F-7019 |  | D004 | C-130J ADS- | 2020-08-31 |  | Jim Porter |  |  |  | 0 |  | Mariah Callins |  |  | 1 | 1 | U | 2020-08-31 |  | FA8625-18-F-7019NoneD0042020-08-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7162 | C130 | AOA | FA8625-18-F-7162 |  | 4001AD | MAINTENANCE |  |  | Jackie L Macedonia | AT RISK | System/Database Disconnects within LM Systems | No CLIN 4001AD on contract. LM believes this line item is on the OTD list in error. |  |  | Brittany N Scott |  |  | 1 | 1 | J | 2020-07-31 | 2020-07-31 | FA8625-18-F-7162None4001ADNone
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A001 | ICE DETECTO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 0871HM3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A002 | ANTENNA STA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 10-259.10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0022020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A003 | INSULATION | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 10-388527-422 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A004 | SIGNAL COND | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 1221AU1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A005 | MATTRESS AS | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 19260005 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A006 | LINK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 23058078 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A007 | FILTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 23061825 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A008 | NOZZLE ASSY | 2020-07-31 |  | Cindy Failor |  |  |  | 0 |  | Olivia M Haller |  | 23089482 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A009 | COMPUTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 27801-01-03 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A010 | CIRCUIT BRE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 2TC14-2.5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A011 | MICROWAVE O | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 300-1834-01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A012 | ETAC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 304820-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0122020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A013 | AUX VENT VA | 2020-07-31 |  | Cindy Failor | AT RISK | DD250 Accepted In WAWF | DD250 accepted on 2/11, LM coordinating with DCMA to investigate recycling of ELIN. | 0 |  | Olivia M Haller |  | 3291272-2-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A014 | DUCK ASM | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3311278-81 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A015 | CUR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3328558-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0152020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A016 | CUR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3328558-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0162020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A017 | LCK ASSY C | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338700-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0172020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A018 | LCK ASSY C | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338700-6 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0182020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A019 | TOWPLATE AS | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338784-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0192020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A020 | LOCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338863-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0202020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A021 | LOCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338863-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0212020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A022 | SAFETY WALK | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338999-53 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0222020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A023 | SAFETY WALK | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3338999-54 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0232020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A024 | FIRE EXTING | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3341006-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0242020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A025 | FLOOR COVER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3351171-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0252020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A026 | TUBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3351615-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0262020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A027 | ICS CORD | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352003-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0272020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A028 | BRACKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352180-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0282020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A029 | CARRIER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352181-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0292020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A030 | BRACKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3352181-2 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0302020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A031 | STRAP ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3353439-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0312020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A032 | RAIL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3355574-8 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0322020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A033 | TANK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3357570-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0332020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A034 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3357761-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0342020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A035 | TUBE ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3358516-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0352020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A036 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3365895-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0362020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A037 | PANEL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3365986-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0372020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A038 | RUB STRIP | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 338262-2 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0382020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A039 | RUB STRIP | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 338262-4 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0392020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A040 | POS INDICAT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 364260-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0402020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A041 | TUBE ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 370741-884 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0412020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A042 | TUBE ASM | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 371352-341 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0422020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A043 | BOOSTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 374461-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0432020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A044 | CABLE ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 374943-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0442020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A045 | CABLE ASSY | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -10 |  | Olivia M Haller |  | 376765-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0452020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A046 | LEG ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 382990-13 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0462020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A047 | TUBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 382990-17 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0472020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A048 | VALVE, EJEC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 3D3556-01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0482020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A049 | VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 5145-00-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0492020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A050 | RECEPTACLE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 5256M4 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0502020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A051 | LIFE RAFT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 63880-103 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0512020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A052 | LIFE RAFT | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | -2 |  | Olivia M Haller |  | 63880-104 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0522020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A053 | GEARBOX | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 695700-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0532020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A054 | WINCH | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 695755-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0542020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A055 | CONTROL UNI | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697856-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0552020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A056 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697906-15 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0562020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A057 | RADAR ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697908-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0572020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A058 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697910-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0582020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A059 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697911-17 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0592020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A060 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697913-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0602020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A061 | COPILOT PA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697915-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0612020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A062 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697919-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0622020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A063 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697921-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0632020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A064 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697922-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0642020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A065 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697923-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0652020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A066 | PANEL ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697925-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0662020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A067 | PANEL ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697930-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0672020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A068 | PNL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697936-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0682020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A069 | PANEL | 2020-07-31 |  | Cindy Failor |  |  |  | 0 |  | Olivia M Haller |  | 697939-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0692020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A070 | TRAY MOUNT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697940-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0702020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A071 | BREAKER UN | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected | 0 |  | Olivia M Haller |  | 697941-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0712020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A072 | POWER SPLY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697942-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0722020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A073 | CONTROLLER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697967-7 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0732020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A074 | COMPUTER | 2020-07-31 | 2020-09-30 | Cindy Failor | AT RISK | Supplier Performance | At risk; P-code; PN 697960-9 / SO 10067407 - Mission System Computer | -1 |  | Olivia M Haller |  | 697960-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0742020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A075 | PUBLIC ADRE | 2020-07-31 | 2021-04-30 | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697966-301 / SO 10067406 | -1 |  | Olivia M Haller |  | 697968-301 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0752020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A076 | GRIP ASBY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697976-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0762020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A077 | MFCD | 2020-07-31 | 2021-03-31 | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697977-21 / SO 10067404 | -2 |  | Olivia M Haller |  | 697977-21 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0772020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A078 | FUEL MGT | 2020-07-31 |  | Cindy Failor | AT RISK | Other | At risk; P-code; PN 697980-1 / SO10067403 | -1 |  | Olivia M Haller |  | 697980-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0782020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A079 | FIRESHIELD | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697985-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0792020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A080 | SEAL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697988-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0802020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A081 | VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697966-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0812020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A082 | CHECK VALVE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697998-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0822020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A083 | PNUEMATIC | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 697999-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0832020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A084 | FIRE CONTRO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698009-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0842020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A085 | NACELLE INT | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected / SO #10067452 / PN 698015-5 | 0 |  | Olivia M Haller |  | 698015-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0852020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A086 | PANEL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698024-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0862020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A087 | DUAL SLOT | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698089-5 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0872020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A088 | COMPRESSOR | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698269-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0882020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A089 | DUCK ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698269-9 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0892020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A090 | WATER WASH | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 698270-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0902020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A091 | FILTER | 2020-07-31 |  | Cindy Failor | ON TIME | DD250 Accepted In WAWF | DD250 Accepted in WAWF | 0 |  | Olivia M Haller |  | 808574-3 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0912020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A092 | POWER SPLY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 8ES003417-11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0922020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A093 | INDICATO | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | 95-42-11S6-70397 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0932020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A094 | SPHERE | 2020-07-31 |  | Cindy Failor | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to Contract Dates - On Time DD250 Submittal Expected / PN A802400-10 | 0 |  | Olivia M Haller |  | A802400-10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0942020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A095 | TEST PROBE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | ABC56103-B-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0952020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A096 | FILTER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | AC2291EB10 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0962020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A097 | AIR DATA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | ADA130J723 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0972020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A098 | PLUG FLARED | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | AS5168VV08 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA0982020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A100 | FILTER | 2020-07-31 |  | Cindy Failor | ON TIME | DD250 Accepted In WAWF | Working to Contract Dates - On Time DD250 Submittal Expected | 0 |  | Olivia M Haller |  | D9-155-1 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1002020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A101 | THERMOCOUPL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | HMCL150/P1/5K | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1012020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A103 | PLUG | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA6T25W8SCL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1032020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A104 | PLUG | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA6T25W8SEL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1042020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A105 | RECEPTACLE | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | KJA7T21W75PAL | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1052020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A106 | ANTENNA | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LG81CE01 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1062020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A107 | TERMINAL | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS35076-3-03 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1072020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A108 | PANEL ASSY | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS35310B02AY | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1082020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A109 | WASHER | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | LS5984D08M | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1092020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A110 | PIN | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | NAS1366S7S11 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1102020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A111 | SINGAL COND | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | NCAL52K0/500F | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1112020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A113 | RESISTOR | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | RNC65H1003FRF | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1132020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-18-F-7801 | C130 | AOA | FA8625-18-F-7801 |  | A114 | GASKET | 2020-07-31 |  | Cindy Failor | AT RISK |  |  | 0 |  | Olivia M Haller |  | SG278000-02 | 1 | 1 | J | 2020-07-31 |  | FA8625-18-F-7801NoneA1142020-07-31 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-08-03 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-08-03 |  | FA8625-19-F-7033None00082020-08-03 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-09-01 |  | Jim Porter | AT RISK |  |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-09-01 |  | FA8625-19-F-7033None00082020-09-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-06-08 |  | Jim Porter | AT RISK |  |  | 0 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-06-08 |  | FA8625-19-F-7033None00082020-06-08 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0008 | 8 ENGINE/AP | 2020-07-07 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | 0 | Daniel L Kiefer | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-07-07 |  | FA8625-19-F-7033None00082020-07-07 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-08-03 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-08-03 |  | FA8625-19-F-7033None00092020-08-03 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-09-01 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | -1 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-09-01 |  | FA8625-19-F-7033None00092020-09-01 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-06-08 |  | Jim Porter | ON TIME | DD250 Accepted In WAWF |  | 0 |  | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-06-08 |  | FA8625-19-F-7033None00092020-06-08 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 0009 | 8 WIRE INST | 2020-07-07 |  | Jim Porter | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | SUBMITTED TO WAWF ON 5/28/2020 | 0 | Daniel L Kiefer | Mary Kate Chaney |  |  | 1 | 1 | J | 2020-07-07 |  | FA8625-19-F-7033None00092020-07-07 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8625-19-F-7033 | C130 | AOA | FA8625-19-F-7033 |  | 1423DD |  |  |  | Jim Porter | AT RISK |  |  |  |  | Mary Kate Chaney |  | DATA | 1 | 1 | J | 2020-09-01 | 2020-09-01 | FA8625-19-F-7033None1423DDNone
ALX | TBD | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B001 | CREW SEAT A | 2020-06-30 | 2020-04-30 | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0005) on 4/21/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 3A067-0010-02 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169NoneB0012020-06-30 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B002 | BELT,SAFETY | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0004) on 1/13/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 54H19651 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169NoneB0022020-06-30 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B003 | HARNESS | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0002) on 1/13/20 and parts shipped | 0 | Mark P Lewandowski | Brittany N Scott |  | 57D677 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169NoneB0032020-06-30 00:00:00
ALX | TBD | FA8625-16-D-6458 | FA8629-18-F-7169 | C130 | AOA | FA8629-18-F-7169 |  | B004 | 12'SEAT RAC | 2020-06-30 |  | Jackie L Macedonia | ON TIME | DD250 Accepted In WAWF | DD250'd (CVA0003) on 11/22/19 and parts shipped | 0 |  | Brittany N Scott |  | LS5301 | 1 | 1 | J | 2020-06-30 |  | FA8629-18-F-7169NoneB0042020-06-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0001 | C-5M CNS/AT | 2020-09-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected |  | -1 |  | Nalysha S Jones | C-5M CNS/ATM INTEGRATION, DESIGN AND DEVELOPMENT |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589None00012020-09-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0007 | OPERATIONAL | 2020-09-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | CLIN0007 extended to 30SEPT | -1 | Matt Tyler | Nalysha S Jones | OPERATIONAL LEVEL AND PROGRAMMED DEPOT MAINTENANCE TECHNICAL ORDERS/MANUALS |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589None00072020-09-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0015 | CNS/ATM TRA | 2020-07-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Submitted CoC Thursday, NOC Friday. | 0 | Matt Tyler | Nalysha S Jones | CNS/ATM TRAVEL |  | 1 | 1 | U | 2020-07-30 |  | FA8625-17-C-6589None00152020-07-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0016 | TECHNICAL D | 2020-06-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to contract dates | -1 | Matt Tyler | Nalysha S Jones | TECHNICAL DATA PACKAGE (TDP) FOR WEAPON SYSTEM TRAINERS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589None00162020-06-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0018 | FINAL TECHN | 2020-06-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to contract dates | -1 | Matt Tyler | Nalysha S Jones | FINAL TECHNICAL DATA PACKAGE (TDP) FOR WEAPON SYSTEM TRAINERS |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589None00182020-06-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0019 | WEAPON SYST | 2020-06-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to contract dates | -1 | Matt Tyler | Nalysha S Jones | WEAPON SYSTEM TRAINER MODIFICATION |  | 1 | 1 | U | 2020-06-30 |  | FA8625-17-C-6589None00192020-06-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0026 | UPDATE OF M | 2020-09-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | Working to contract dates | -1 | Matt Tyler | Nalysha S Jones | UPDATE OF MAINTENANCE QUAL TRAINING MATERIALS (AFTER OT&E) |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589None00262020-09-30 00:00:00
ALQ | AMMM | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 0027 | INITAL CADR | 2020-07-30 |  | Matt Tyler | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | COC Submitted to USAF, Awtg PCO Concurrence to Close | 0 | Matt Tyler | Nalysha S Jones | INITIAL CADRE QUAL MAINTENANCE TRAINING AND MATERIAL |  | 1 | 1 | U | 2020-07-30 |  | FA8625-17-C-6589None00272020-07-30 00:00:00
ALQ | TBD | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | 1423DD | DATA |  |  | Matt Tyler | [5 empty] | Nalysha S Jones |  |  | 1 | 1 | U | 2020-09-30 | 2020-09-30 | FA8625-17-C-6589None1423DDNone
ALQ | TBD | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | B001 | DATA | 2020-09-30 |  | Matt Tyler |  |  |  | 0 |  | Nalysha S Jones |  |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589NoneB0012020-09-30 00:00:00
ALQ | TBD | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | B002 | DATA | 2020-09-30 |  | Matt Tyler | AT RISK |  |  | -1 | Matt Tyler | Nalysha S Jones |  |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589NoneB0022020-09-30 00:00:00
ALQ | TBD | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | C009 | DATA | 2020-09-30 |  | Matt Tyler |  |  |  | 0 |  | Nalysha S Jones |  |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589NoneC0092020-09-30 00:00:00
ALQ | TBD | FA8625-17-C-6589 |  | C5 | AOK | FA8625-17-C-6589 |  | C018 | DATA | 2020-09-30 |  | Matt Tyler | AT RISK |  |  | -3 | Matt Tyler | Nalysha S Jones |  |  | 1 | 1 | U | 2020-09-30 |  | FA8625-17-C-6589NoneC0182020-09-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AB | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  | Kit accepted to W09 - Bonded Storage on 9/27/2019 | 0 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-0061None0208AB2020-07-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AC | Supplementa | 2020-07-30 |  | Nick Kljucaric | AT RISK |  |  | 0 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-0061None0208AC2020-07-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AD | Supplementa | 2020-07-30 |  | Nick Kljucaric | ON TIME |  | On Track - Material shortage were resolved. The parts have been received. | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-0061None0208AD2020-07-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AE | Supplementa | 2020-07-30 |  | Nick Kljucaric | ON TIME |  | On Track - Material shortage were resolved. The parts have been received. | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-0061None0208AE2020-07-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0208AF | Supplementa | 2020-07-30 |  | Nick Kljucaric | ON TIME |  | On Track - Material shortage were resolved. The parts have been received. | -1 | Doug McNamee | Reda R Belmaachi | SUPPLEMENTAL KIT |  | 1 | 1 | J | 2020-07-30 |  | N00019-17-C-0061None0208AF2020-07-30 00:00:00
ALT | AMMM | N00019-17-C-0061 |  | C130 | AOR | N00019-17-C-0061 |  | 0302AD | AFT Sensor | 2020-07-31 |  | Nick Kljucaric | ON TIME |  | P/N 3366408-3; SO 10113522; | -3 | Doug McNamee | Reda R Belmaachi | AFT SENSOR COVER PLATE | 3366408-3 | 1 | 1 | J | 2020-07-31 |  | N00019-17-C-0061None0302AD2020-07-31 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AB | EMU | 2020-06-01 | 2020-03-16 | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82859098 / CVA0030; PN 100-601978-401 / SO 10108634 | 0 | Philip C Bailey | Reda R Belmaachi | ELECTRONIC MODULE, STANDARDIZED P/N 100-601978-401 |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AB2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AC | PMD | 2020-06-01 | 2020-06-01 | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 83050069; PN 100-604003-054 / SO 10108633 | 0 | Philip C Bailey | Reda R Belmaachi | DISPLAY UNIT, FLIGHT INFORMATION |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AC2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AF | HAND MICROP | 2020-06-01 |  | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82735316; PN 18226G15; SO 10108630 | 0 | Philip C Bailey | Reda R Belmaachi | MICROPHONE, DYNAMIC |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AF2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AG | DIGITAL SWI | 2020-06-01 |  | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82735317; 82735570; PN 2292643-500; SO 10108629 | 0 | Philip C Bailey | Reda R Belmaachi | DIGITAL SWITCHING UNIT |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AG2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AH | PMD TETHER | 2020-06-01 |  | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82735318; PN 245-604320-001; SO 10108628 | 0 | Philip C Bailey | Reda R Belmaachi | CABLE ASSEMBLY, SPECIAL PURPOSE, ELECTRICAL |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AH2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AM | PANEL ASSY | 2020-06-01 | 2020-06-01 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; 2ea DO 83054231, 2ea DO 83056044; PN 3365972-1 / SO 10108624 | 0 | Philip C Bailey | Reda R Belmaachi | PANEL, INDICATOR |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AM2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AN | PRG INT BLA | 2020-08-01 |  | Nick Kljucaric | ON TIME | DD250 Accepted In WAWF | Closed; DO 82735322; CVA CVA0023; P/N 357048-001 | 0 | Philip C Bailey | Reda R Belmaachi | BLANKING UNIT |  | 1 | 1 | J | 2020-08-01 |  | N00019-19-F-4193None0005AN2020-08-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005AZ | ANTENNA AS | 2020-06-01 |  | Nick Kljucaric | AT RISK | Other | At risk; HUD -- P-coded; PN 697940-25 / SO 10108611 | 0 | Philip C Bailey | Reda R Belmaachi | ANTENNA ASSY |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005AZ2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BA | HUD ELECTRO | 2020-06-01 |  | Nick Kljucaric | AT RISK | Other | Late Letter Notification Delivered on June 9, 2020. At risk; HUD -- P-coded; PN 697940-25 / SO 10108611; Labeling Issues; No ECD available. | -4 | Philip C Bailey | Reda R Belmaachi | ELECTRONIC COMPONENTS ASSEMBLY |  | 1 | 1 | J | 2020-06-01 |  | N00019-19-F-4193None0005BA2020-06-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BC | PILOT CONTR | 2020-09-01 |  | Nick Kljucaric | ON TIME |  | PN 698261-1 / SO 10108609 | -4 | Philip C Bailey | Reda R Belmaachi | PILOT CONTROL ASSEMBLY CONTROL WHEEL, AIRCRAFT |  | 1 | 1 | J | 2020-09-01 |  | N00019-19-F-4193None0005BC2020-09-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BF | VIDEO SWITC | 2020-09-01 |  | Nick Kljucaric | ON TIME |  | PN 698267-1 / SO 10108606 | -4 | Philip C Bailey | Reda R Belmaachi | SWITCH, ELECTRONIC (VIDEO SWITCH) |  | 1 | 1 | J | 2020-09-01 |  | N00019-19-F-4193None0005BF2020-09-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-19-F-4193 | C130 | AOR | N00019-19-F-4193 |  | 0005BR | VHF DATA RA | 2020-09-01 |  | Nick Kljucaric | ON TIME |  | PN 965-1696-081 / SO 10108596 | -3 | Philip C Bailey | Reda R Belmaachi | VHF DATA RADIO |  | 1 | 1 | J | 2020-09-01 |  | N00019-19-F-4193None0005BR2020-09-01 00:00:00
ALT | AMMM | N00019-19-D-0014 | N00019-20-F-0852 |  | AOF | N00019-20-F-0852 |  | 0105AC | CS AMP | 2020-09-25 | [5 empty] | -16 |  |  | CS AMP |  | 1 | 1 | J | 2020-09-25 |  | N00019-20-F-0852None0105AC2020-09-25 00:00:00
ALA | TBD | N00383-19-F-Q50L |  | C130 | AOI | N00383-19-F-Q50L |  | 0005AA | UPPER BUNK | 2020-07-02 | 2020-07-02 | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 82973504; PN 3353181-5 / SO 10107891 | 0 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-07-02 |  | N00383-19-F-Q50LNone0005AA2020-07-02 00:00:00
ALA | TBD | N00383-19-F-Q50R |  |  | AOI | N00383-19-F-Q50R |  | 0003AA | GLARESHIELD | 2020-09-21 |  | Nicholas J Kljucaric | ON TIME |  | P/N 3350008-11; S/O 10108289 | -1 | Philip C Bailey | Leesa A Blair |  |  | 1 | 1 | J | 2020-09-21 |  | N00383-19-F-Q50RNone0003AA2020-09-21 00:00:00
ALL | AMMM | N00383-19-P-D125 |  | C130 | AOI | N00383-19-P-D125 |  | 0001AA | INTERFACE U | 2020-08-06 |  | Nicholas J Kljucaric | AT RISK |  |  | -4 | Philip C Bailey | Reda R Belmaachi | EVALUATE, REPAIR AND/OR MODIFY P/N 698258-7 |  | 1 | 5 | J | 2020-08-06 |  | N00383-19-P-D125None0001AA2020-08-06 00:00:00
ALL | AMMM | N00383-19-P-D151 |  | C130 | AOI | N00383-19-P-D151 |  | 0001AA | COOLER,LUBR | 2020-09-28 |  | Nick Kljucaric | AT RISK |  |  | -4 |  | Reda R Belmaachi | EVALUATE, REPAIR AND/OR MODIFIY PN 697997-1 LUBRICATING COOLER |  | 1 | 5 | J | 2020-09-28 |  | N00383-19-P-D151None0001AA2020-09-28 00:00:00
ALL | AMMM | N00383-19-P-D151 |  | C130 | AOI | N00383-19-P-D151 |  | 0001AB | COOLER,LUBR | 2020-09-28 |  | Nick Kljucaric | AT RISK |  |  | -4 |  | Reda R Belmaachi | EVALUATE, REPAIR AND/OR MODIFIY PN 697997-1 LUBRICATING COOLER |  | 1 | 5 | J | 2020-09-28 |  | N00383-19-P-D151None0001AB2020-09-28 00:00:00
ALA | TBD | N00383-20-F-Q503 |  | C130 | AOI | N00383-20-F-Q503 |  | 0004AA | FITTING, ST | 2020-08-24 |  | Nick Kljucaric | ON TIME |  | PN 3351230-21 / SO 10109808; DO# 83109118 DD250# CVA0003 | -1 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-08-24 |  | N00383-20-F-Q503None0004AA2020-08-24 00:00:00
ALA | TBD | N00383-20-F-Q503 |  | C130 | AOI | N00383-20-F-Q503 |  | 0006AA | SEAT COVER | 2020-07-24 | 2020-07-24 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 83032368, PN 1A067-0125CS / SO 10109811 | 0 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-07-24 |  | N00383-20-F-Q503None0006AA2020-07-24 00:00:00
ALA | TBD | N00383-20-F-Q505 |  | C130 | AOI | N00383-20-F-Q505 |  | 0001AA | COUPLER NET | 2020-08-26 |  | Nick Kljucaric | ON TIME |  | PN LN72000-18 / SO 10110366; DO# 83109122 DD250# CVA0003 | -1 | Philip C Bailey | Reda R Belmaachi |  |  | 1 | 1 | J | 2020-08-26 |  | N00383-20-F-Q505None0001AA2020-08-26 00:00:00
ALA | TBD | SPE4A5-19-F-08R5 |  |  | AOI | SPE4A5-19-F-08R5 |  | 0001 | BAG,ENGINE | 2020-09-04 |  | Nicholas J Kljucaric | ON TIME |  | PN ATL1175-001G / SO 10108448 | -19 | Philip C Bailey | Mary Kathleen Chaney |  | 0079133061 | 1 | 1 | J | 2020-09-04 |  | SPE4A5-19-F-08R5None00012020-09-04 00:00:00
ALA | TBD | SPE4A5-19-F-09L6 |  |  | AOI | SPE4A5-19-F-09L6 |  | 0001 | TUBE,BENT,M | 2020-08-07 |  | Nicholas J Kljucaric | AT RISK |  | S/O 10108449; Delayed due to COVID-19; Modification has been requested. | -13 | Philip C Bailey | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-07 |  | SPE4A5-19-F-09L6None00012020-08-07 00:00:00
ALA | TBD | SPE4A5-19-F-356F |  |  | AOI | SPE4A5-19-F-356F |  | 0001 | LEADING EDG | 2020-09-30 |  | Nicholas J Kljucaric | ON TIME |  | P/N 370019-3S; S/O 10106699 | -7 | Philip C Bailey | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-09-30 |  | SPE4A5-19-F-356FNone00012020-09-30 00:00:00
ALA | TBD | SPE4A5-19-F-900X |  |  | AOI | SPE4A5-19-F-900X |  | 0001 | TUBE,BENT,M | 2020-06-30 | 2020-06-30 | Nicholas J Kljucaric | AT RISK | More Investigation Needed | PN 3354434-1 / SO 10107795; Vendor Shut Down due to COVID-19; Just started Full Production; Modification has been requested. | -24 | Philip C Bailey | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-06-30 |  | SPE4A5-19-F-900XNone00012020-06-30 00:00:00
ALA | TBD | SPE4A5-19-F-901L |  |  | AOI | SPE4A5-19-F-901L |  | 0001 | DOOR,ACCESS | 2020-09-21 |  | Nicholas J Kljucaric | AT RISK |  |  | -1 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-09-21 |  | SPE4A5-19-F-901LNone00012020-09-21 00:00:00
ALA | TBD | SPE4A5-19-F-904P |  |  | AOI | SPE4A5-19-F-904P |  | 0001 | TUBE,BENT,M | 2020-08-17 |  | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | S/O 10108288; P/N 3354435-1 | -4 | Philip C Bailey | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-17 |  | SPE4A5-19-F-904PNone00012020-08-17 00:00:00
ALA | TBD | SPE4A5-19-F-905Q |  |  | AOI | SPE4A5-19-F-905Q |  | 0001 | WIRING HARN | 2020-09-21 |  | Nicholas J Kljucaric | AT RISK |  |  | -6 |  | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-09-21 |  | SPE4A5-19-F-905QNone00012020-09-21 00:00:00
ALA | TBD | SPE4A5-20-F-0075 |  | C130 | AOI | SPE4A5-20-F-0075 |  | 0001 | HOLDER,CHAR | 2020-09-25 |  | Nick Kljucaric | AT RISK |  |  | -5 | Audrey L Clark |  |  |  | 1 | 1 | J | 2020-09-25 |  | SPE4A5-20-F-0075None00012020-09-25 00:00:00
ALA | TBD | SPE4A5-20-F-3953 |  | C130 | AOI | SPE4A5-20-F-3953 |  | 0001 | BOX,SHIPPIN | 2020-07-09 | 2020-05-31 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | On track; DO 82980890; PN 3354968-1 / SO 10109306 | -476 | Philip C Bailey |  |  |  | 1 | 1 | J | 2020-07-09 |  | SPE4A5-20-F-3953None00012020-07-09 00:00:00
ALA | TBD | SPE4A5-20-F-6636 |  | C130 | AOI | SPE4A5-20-F-6636 |  | 0001 | BAG,ENGINE | 2020-07-21 | 2020-07-21 | Nick Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | In Process; PN ATL1175-001G / SO 10109851/DO# 83075966; CVA0001Z | -11 | Philip C Bailey |  |  |  | 1 | 1 | J | 2020-07-21 |  | SPE4A5-20-F-6636None00012020-07-21 00:00:00
ALA | TBD | SPRPA1-19-F-Q504 |  |  | AOI | SPRPA1-19-F-Q504 |  | 0001AA | FLAP ASSY | 2020-08-06 |  | Nicholas J Kljucaric | ON TIME | Working to Contract Dates - On Time DD250 Submittal Expected | S/O 10104209; 3352602-2, DO# 8289400 (QTY 1) | -1 | Philip C Bailey | Mary Kathleen Chaney |  |  | 1 | 1 | J | 2020-08-06 |  | SPRPA1-19-F-Q504None0001AA2020-08-06 00:00:00
[7 empty] | Count: | 921 | [17 empty] | NoneCount:921None
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone
NoneNoneNoneNone